## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Update inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time. RVCOG if needed. | Report on new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks with stations. Add a percentage of stations added until 100% of parks have stations. | DMAs to fill in any updates. For all DMAs, the planned dog park stations have been completed at the parks. As new parks are planned and built, additional stations that are added will be documented in the annual report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volumes (Post construction). | Continue to incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff through municipal codes and ordinances. | Staff Time, Work with RVCOG for tracking and funding support for projects (grants, partnerships) | Track the features installed, size and treatment expectations as they are installed by updating the LID map annually. | Ongoing as development occurs. | In Phase II report. Limited tracking and mapping completed by the Regional Manager (RVCOG) as requested. | The Regional Manager (RM) electronic survey form is available to inventory and map features (https://arcg.is/1zbb5e) that was created for regional use and will inventory DMAs as requested. Most annual work is completed under local Phase II programs and included in their annual MS4 reports. Any tracking and/or other information collected by the RM is included in the annual reports and added to these forms. In addition, online maps show up to date tracking (https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=018eec42042b4216b7812956b974593f). No sites were inventoried by the RM in 2023-2024. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide educational opportunities including hands-on activities, resources, articles in newsletters/publications, and/or promote local workshops. | Staff time, Work with RVCOG, Partners. | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Summarize overall activity including number of projects: number of downspouts disconnected, rain gardens constructed, and participants. | General information, workshops, volunteer opportunities, and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/) which includes a copy of the 2023-2024 Regional Stormwater Annual Report for Education and Public Involvement, and information on the TMDL page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/). Most of the work completed in 2023-2024 under the TMDL program was on pollinator gardens which provide many of the benefits of the rain gardens, but are not specifically designed for that purpose. Pollinator gardens that were worked on or maintained include: Railroad Park, Medford Sports Park, Cascade Christian High School, and Peninger Road. The RM did lead a workshop at TRAILS outdoor school in Ashland that included a detailed discussion of stormwater management including the many features found on campus. Additional details on the program can be found in the Phase 2 Education and Outreach Report (https://rvcog.org/wp-content/uploads/2024/08/Annual-Report-2023-2024_8_28_24.pdf). In addition, resources a link to the Regional Stormwater Design Manual, the Rain Garden Guide (https://www.stream-smart.com/wp-content/uploads/2020/07/Rain-Garden-Guide.pdf) and the Planting for Stormwater Quality brochure (https://www.stream-smart.com/wp-content/uploads/2023/02/Planting-For-Stormwater-Quality.pdf) are available on the Stream Smart Website. | Year 1: July 2020-June 2020
Year 2: July 2021-June 2021
Year 3: July 2022-June 2022
Year 4: July 2023-June 2023
Year 5: July 2024-June 2024
|  | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RM during the implementation year. Jackson SWCD does have a stormwater rebate program which could be used to fund smaller scale BMPs and was promoted as an option for the region. The RM will work with the DMAs as requested to evaluate potential funding for BMP implementation and apply for funding. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Municipal Operations | Implement Stormwater Management Practices as time and funding permits. Examples activities include: Good Housekeeping, fleet maintenance, street sweeping, and site control (erosion) to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. In Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). Part of Regional Monitoring Program. | Review and refine illicit discharge and hot spot water sampling program as needed. Participation in the regional TMDL programs addresses sampling of storm drains to evaluate their impact on TMDL pollutant levels, tracking and investigation of concerns as needed (or requested) especially related to TMDL concerns, and serving as a point of contact for water quality concerns. | Staff Time | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, Annual report or regional activities generated by RVCOG. | As part of the TMDL program, the RM conducts visual inspections of storm drains as part of the stormwater monitoring program. Storm drain information is documented using survey forms and mapped. The visual data collected during the storm drain runs can be on the following map (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=573be1211ff644ed8d19c470f155fff1). The most recent survey was completed on July 17th, 2024 as part of the storm drain dry run. For the 2023-2024 monitoring season, the survey was completed in June of 2023. As part of the TMDL monitoring program, the RM visited 50 storm drains during the implementation period and collected 37 samples from storm drains. Some of the storm drains do not flow (especially during the low flow period), and some drains are unsafe to access at particular flows or due to overgrowth of weeds. Abnormally high readings of E/coli and other parameters are reported to the DMA and followed up on as needed as part of the hot spot monitoring program. In 2023-2024 reports were made to RVSS and Phoenix (bacteria levels at Blue Heron Park - TMDL site in February of 2024). The TMDL program also has a "hot spot" monitoring program to assist in identifying illicit discharges in partnership with the MS4 program or to serve as a major part of an IDDE program for jurisdictions that don't have their own programs (e.g., Jacksonville). Observations made are documented and reported to the appropriate DMA, agency, or OERS. A contact list is updated and distributed annually to the DMAs to help with communications between DMAs and also with the public. In addition, the RM investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). Concerns and actions are also documented in the activity summary tab and presented at quarterly TMDL meetings (by the RM, DEQ, and other as part of the TMDL Roundtable/Updates). Hot spot reports included a report of oil into a storm drain in Medford (December 2023), materials observed in two location in the White City Network to RVSS, MWC, and DEQ (December 2023), and Elk Creek to RVSS, Central Point, and Medford in April and May 2024. Concerns and actions are also documented in the activity summary tab. The Stream Smart website also contains information on reporting spills and contains the contact sheets (shown in the contact sheet tab). | Year 1: July 2020-June 2021
|  |  | Continued participation in regional program through RVCOG. |  |  |  |  | Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Part of phase Ii compliance. | Ongoing | Update on the number of investigations and any enforcement actions taken. Any activities tracked or responded to by RVCOG are including in the annual report of regional activities. | The RM investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). 8 sites were logged this year. Details are provided above and in the referenced files and sheets. Example pictures are included in the hot spot tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. This could be summarized in the NPDES Phase II program report if applicable. | DMAs to fill in any updates. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RM during the implementation year are reported to the appropriate DMA, MS4, and/or DEQ. Concerns and actions are also documented in the activity summary tab. Data collected by the TMDL monitoring program is reviewed quarterly and sent to DMAs. Areas of abnormally high bacteria are discussed with DMAs and followed up on as needed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time. RVCOG. Partners | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Monitoring data collected as part of the TMDL program and some additional sampling collected to evaluate contributions and impacts from the fire (including bacteria concerns) continue to keep tabs on the post fire restoration actions. 271 samples were collected by the monitoring program this year and include bacteria and other parameters of interest to the TMDL program. In addition, a comprehensive two year monitoring program funded by OWEB to study the long term impacts of the fire and look at where restoration efforts need to be focused and on what parameters was completed. Monitoring data collected as part of the normal TMDL and storm drain runs was used as part of the study. In addition, the TMDL program is providing in kind match to the monitoring program in data collection and analysis with the existing program and by collecting additional sampling in conjunction with ongoing monitoring runs. Data collected includes comprehensive metals and nutrients, 6 PPD Quinone, diesel and other hydrocarbons, and HABS (summer 2022). Over 300 samples were collected by the monitoring program this year and include bacteria and other parameters of interest to the TMDL program. In addition, there are several local efforts that are looking at ways to work on keeping the creeks cleaner and to continue with investigations of storm drains. For example, in May of 2024 there was a large effort undertaken by the City of Medford, the Community Livability Team, the RM, Plant Oregon, and others to clean-up trash from a large camp that is on the banks of Bear Creek. This effort was the first in working on a solution to removing the trash that enters to stream and also the impacts of camps which can included bacteria. In addition, there was an initial meeting of the Aquatic Trash Prevention Partnership in June which is looking at ways to increase awareness of trash and other materials entering Bear Creek including bacteria by focusing on pollution prevention. There is also continuing discussion on the next steps for investigation high bacteria levels in storm drains. There was analysis of data by DEQ with support from the RM that was presented at TMDL meetings. Several storm drains that result in consistently high bacteria levels are being discussed for follow up in future TMDL years. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025