## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Update inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time. RVCOG if needed. | Report on new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks with stations. Add a percentage of stations added until 100% of parks have stations. | DMAs to fill in. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volumes (Post construction). | Continue to incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff through municipal codes and ordinances. | Staff Time, Work with RVCOG for tracking and funding support for projects (grants, partnerships) | Track the features installed, size and treatment expectations as they are installed by updating the LID map annually. | Ongoing as development occurs. | In Phase II report. Limited tracking and mapping completed by the Regional Manager (RVCOG) as requested. | The Regional Manager (RM) electronic survey form is available to inventory and map features (https://arcg.is/1zbb5e) that was createdf for regional use and will inventoryu DMAs as requested. Data collected by the survey can be found in the Tracking Map and Survey tab. Most annual work is completed under local Phase II programs and included in their annual MS4 reports. All tracking and other information collected by the RM is included in the annual reports in the forms of updates. In addition, online maps show up to date tracking (https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=018eec42042b4216b7812956b974593f). A copy of the map can be seen on the Tracking Mapand Survey tab. No sites were inventoried by the RM in 2022-2023. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide educational opportunities including hands-on activities, resources, articles in newsletters/publications, and/or promote local workshops. | Staff time, Work with RVCOG, Partners. | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Summarize overall activity including number of projects: number of downspouts disconnected, rain gardens constructed, and participants. | General information, workshops, volunteer opportunities, and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/), and information on the TMDL page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/). In the spring of 2023, the pledge feature of the website was update which allowed users to pledge to reduce their impervious surface area. Options for the pledge include disconnecting your downspout and letting flow into a rain garden (https://www.stream-smart.com/how-to-get-involved/pledge/impervious/). A tour of the Pollinator Garden planted in LIthia and Driveway Park was held in September. While not a constructed rain garden, the tour did include discussion of pollinator plants and gardens for home or business use as rain gardens. In addition, the Rain Garden Guide is available on the Stream Smart website (https://www.stream-smart.com/wp-content/uploads/2020/07/Rain-Garden-Guide.pdf). In addition, the Planting for Stormwater Quality brochure (https://www.stream-smart.com/wp-content/uploads/2023/02/Planting-For-Stormwater-Quality.pdf) and a link to the Regional Stormwater Design Manual. | Year 1: July 2020-June 2020
Year 2: July 2021-June 2021
Year 3: July 2022-June 2022
Year 4: July 2023-June 2023
Year 5: July 2024-June 2024
|  | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RM during the implementation year. Jackson SWCD does have a stormwater rebate program which could be used to fund smaller scale BMPs and was promoted as an option for the region. The RM will work with the DMAs as requested to evaluate potential funding for BMP implementation and apply for funding. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Municipal Operations | Implement Stormwater Management Practices as time and funding permits. Examples activities include: Good Housekeeping, fleet maintenance, street sweeping, and site control (erosion) to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. In Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). Part of Regional Monitoring Program. | Review and refine illicit discharge and hot spot water sampling program as needed. Participation in the regional TMDL programs addresses sampling of storm drains to evaluate their impact on TMDL pollutant levels, tracking and investigation of concerns as needed (or requested) especially related to TMDL concerns, and serving as a point of contact for water quality concerns. | Staff Time | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, Annual report or regional activities generated by RVCOG. | As part of the TMDL monitoring program, the RM conducts visual inspections of storm drains as part of the stormwater monitoring program and documents observations using Survey 1-2-3 and mapped on ArcGIS. No concerns were noted during visual inspections. The last survey 1-2-3 documented inspection was completed in June 2023. Data collected can be found on the following map (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=573be1211ff644ed8d19c470f155fff1). As part of the TMDL monitoring program, the RM collected 34 samples from storm drains. Abnormally high readings of E.coli and other parameters are reported to the DMA and followed up on as needed as part of the hot spot monitoring program (e.g., bacteria levels on SD9 to the City of Medford). Overall, 65% of the samples collected exceeded the bacteria standard and 96% of the samples exceeded the phosphorus standard. The RM also serves as a point of contact for regional water quality concerns. Contact made are documented and reported to the appropriate DMA, agency, or OERS. A contact list is updated and distributed annually to the DMAs and is also available online. The Stream Smart website also contains information on reporting spills and contains the contact sheets (shown in the contact sheet tab). In addition, the RM investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). Concerns and actions are also documented in the activity summary tab and presented at quarterly TMDL meetings (by the RM, DEQ, and other as part of the TMDL Roundtable/Updates). | Year 1: July 2020-June 2021
|  |  | Continued participation in regional program through RVCOG. |  |  |  |  | Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Part of phase II compliance. | Ongoing | Update on the number of investigations and any enforcement actions taken. Any activities tracked or responded to by RVCOG are including in the annual report of regional activities.. | The RM investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). Observations for 2022-2023 included the bacteria in the 10th Street Storm Drain, and black discharge in storm drain ditches and waterways in White City. In addition, the RM received calls regarding a residents concern regarding a retaining wall in Lone Pine Creek in Medford, water quality above the reservoir in Ashland. While outside of the Bear Creek watershed, the RM analyzed 2 samples of bacteria in Elk Creek to address some local concerns and also regarding algae in a pond from an Eagle Point resident. The algae concern was referred to Jackson SWCD. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. This could be summarized in the NPDES Phase II program report if applicable. |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RM during the implementation year are reported to the appropriate DMA, MS4, and/or DEQ. Concerns and actions are also documented in the activity summary tab. Data collected by the TMDL monitoring program is reviewed quarterly and sent to DMAs. Areas of abnormally high bacteria are discussed with DMAs and followed up on as needed (e.g., SD9). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time. RVCOG. Partners | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Erosion and pollutants from the Almeda and Central Point fire were identified in previous years as a continued concern. As a result, the RM, RVSs, and the BCRI continued to implement restoration projects to help stabilize the area and also kept up with visual monitoring of the area during field work and site visits. In addition, a comprehensive two year monitoring program is underway funded by OWEB to study the long term impacts of the fire and look at where restoration efforts need to be focused and on what parameters. Monitoring data collected as part of the normal TMDL and storm drain runs will be used as part of the study. In addition, the TMDL program is providing match to the monitoring program in data collection and analysis with the existing program and by collecting additional sampling in conjunction with ongoing monitoring runs. Data collected includes comprehensive metals and nutrients, 6 PPD Quinone, diesel and other hydrocarbons, and HABS (summer 2022). Over 300 samples were collected by the monitoring program this year and include bacteria and other parameters of interest to the TMDL program. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025