## Temperature
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Protect riparian areas by implementing current riparian protection standards | Implement current ordinance or riparian buffer standards. | Staff Time | List of actions taken. | Ongoing | Annual reports will track number and type of actions taken. | Comprehensive post fire work continues to be completed along the Bear Creek Corridor. This includes continued management of invasive species along all sections of the corridor, willow staking, pollinator planting, native regeneration, and planting of native species. Much of the work has been completed on public lands along the Greenway, although there has been some work completed on private lands as well. While not directly related to ordinance enforcement, all these activities meet requirements of local ordinances. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for restoration projects. This is a regional task in collaboration with RVCOG and/or other local groups. | Line item established in budget with annual funding. | first year program development and discussion, with line item and funding pending annually thereafter if program is established | Planting statistics, leveraged funding (including in-kind), and/or projects. This portion focuses on the implementation of restoration projects and builds on the DMA wide restoration program. Work on this program has been completed through funding leveraged by the RM and their coordination of and working through the Bear Creek Restoration Initiative (BCRI)in addition to completing work for the TMDL and Stream Smart Programs. | No specific line item was established for restoration activities for this implementation cycle (5-year plan). TMDL funding provides general support and match for riparian restoration activities including but not limited to identifying and prioritizing areas needing restoration, mapping areas (identified, prioritized, in process, and/or completed), developing planting plans/recommendations, management of invasive species, organizing and participating in volunteer activities, planting native species (containers, cuttings, stakes), applying for grants, coordinating with other groups for restoration (including coordinating the BCRI group), and management of specific projects. Primary funding for on-the-ground implementation is leveraged through grants, volunteers, and partners. A list of all funding leveraged including restoration is included in the funding tab. RVCOG (RM) participates in and coordinates the Bear Creek Restoration Initiative (BCRI) which is a group focused on restoring the Bear Creek Corridor as an entire unit/corridor by starting with the highest priority sites. In addition, the RM participates in and/or coordinates the restoration working group, the stakeholder engagement working group, and the pollinator working group. The TMDL implementation program plays a vital role in the program and the RM represents this program for the TMDL and Stream Smart programs. Information on the BCRI program can be found online at https://bcri.squarespace.com/, on the Stream Smart website (https://www.stream-smart.com/bear-creek-restoration-initiative/), or RVCOG's website (https://rvcog.org/bear-creek-restoration-initiative/). Restoration activities completed this year included planting of pollinator species in several gardens and restoration projects, willow staking, distribution of ponderosa pines for planting, and prioritization of planting sites for pollinators. In addition the RM completed interactive maps highlighting restoration projects and activities of BCRI. Approximately 3,750 plugs and trees were planted in Bear Creek of this program. In addition, appriximately 300 acres of invasive species were treated with funding provided by Jackson County. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. The regional program builds on the work completed in previous years and uses materials found in Bear Creek and Rogue Basin Planting Plans to prioritize and begin implementation. | Continue to participate in the regional program through RVCOG. | Completion and record of annual efforts (map updates, statistics, funding) | Annually | Provide updates on the status of sites in each DMA, new sites identified and prioritized, costs, schedule, and other logistics. Develop an annual goal for restoration (e.g., number of trees planted, miles restored, etc.). Outreach covered under the Education and Outreach Section. | The RM has been working with the BCRI and local communities to develop and implement riparian restoration programs and remove invasive species in the Bear Creek Riparian Corridor. New sites for restoration are identified, surveyed using Survey 1-2-3, and mapped annually. By using ESRI mapping featNew this implementation year is the creation of an interactive map that shows restoration projects in Bear Creek identified as part of the RM's TMDL work, by the BCRI, and others (https://rvcog.maps.arcgis.com/apps/instant/interactivelegend/index.html?appid=187846d86be84230b5493c9905e78b7a&locale=en). In addition, the RM mapped ongoing restoration activities in the Bear Creek Riparian Corridor (e.g., restoration projects, invasive species management applications) from a number of sources including the TMDL programs, Jackson County, ODOT, Lomakasti Restoration Project, ODOT, the Freshwater Trust, and the Rogue River Watershed Council. The overall map can be found by here (https://rvcog.maps.arcgis.com/apps/instant/nearby/index.html?appid=cb4c5e87389944f193b1c0e29e4a4c5b ). Maps are being refined to focus in on different areas of the corridor and also by theme. Specific restoration statistics can be found in the Willow Staking tab and the Other Restoration _Planting tab. The annual goal of planting a minimum of 500 trees and shrubs was achieved. As part of the EPA Technical Assistance funding received ((Wildfire Recovery Assistance for Oregon), the RM and members of BCRI restoration group completed the Bear Creek Natural Resources Plan (https://www.stream-smart.com/wp-content/uploads/2023/05/Bear-Creek-Final-NRP-Compiled_04.14.23.pdf). The concepts are being expanded for application across the Bear Creek Riparian Corridor. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Volunteer Planting Event(s) | City participates in events: Events may include at least one featured tree planting project or tree giveaways to residents. Events will be planned in the community, as part of an event (e.g. Fall Festival, Earth Day), incorporated into Salmon Watch (riparian section), and/or planned as a regional event. | Staff time. RVCOG. Partners. And/or volunteers. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | A minimum of one event held each year with local participants and activities that educate and implement tree planting. | Five events were held this implementation year involving planting in addition to the distribution of 500 ponderosa pines for planting in the watershed. Activities included two willow stakings (Lone Pine Creek and Coleman Creek/North Ridge Terrace), two pollinator planting events (one with Phoenix High School at Blue Heron park and one with volunteers at the Pollinator Garden at Lithia and Driveway park), and a pine planting in Central Point by Crater Renaissance Academy as part of the Adopt-A-Greenway Program. In addition, plants (pollinator species) were provided to Cascade Christian High School. An estimated 3000 willow stakes were planted in addition to the 500 pines provided and 250 other species for a total of 3,750 species planted this implementation year. Information on the events including number of volunteers, stakes planted, and other information can be found on the Restoration Volunteers tab. https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=4736299ed1a041ac87b70d4cafa4c4eb | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publically owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time. Regional participation with RVCOG. Partnerships with local groups. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify (map) Implemented projects on an annual basis until 100% complete. If all public lands are completed, maintain plantings and add any new areas that become public. | The Almeda fire altered the strategies and priorities of restoration throughout the riparian corridor impacting TMDL planned sites, BCRI priorities, and partner priorities. Post fire public lands are being restored as high priorities. In addition, maps have been updated with restoration information including implemented projects on public lands. The Riparian Conditions (RC) maps show strategies along the corridor that are beginning to undergo implementation. Riparian Maps and their descriptions are located at https://rvcog.org/bear-creek-restoration-maps/. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Stormwater Runoff | Reduce warm stormwater runoff volumes (post construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from streets, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects that incorporated LID or other methods into development and redevelopment plans |  | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals including identification of new invasive species of concern and control methods and new restoration techniques. | Staff time. Regional programs through RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The focus of adaptive management related to restoration has been in continued development of strategies for restoring riparian areas after fires including ongoing management of invasive species in the areas that burned and in between (areas that didn't that pose a high risk) including long term management. As a collective, the RM participating in (and coordinating) the Bear Creek Restoration Initiative (BCRI) is working on a number of strategies including evaluating the success of native regeneration in the burned area, in creating restoration concepts that balance multipe needs of the corridor, and in implementing these new strategies. The basis for the restoration concepts developed came from participation in the BCRI restoration group and as part of the technical team on a project with EPA (Wildfire Recovery Assistance for Oregon) that led to the completion of the Bear Creek Natural Resources Plan (https://www.stream-smart.com/wp-content/uploads/2023/05/Bear-Creek-Final-NRP-Compiled_04.14.23.pdf). The plan development included a workshop where we developed the initial restoration concepts that are in the plan. The concepts are being expanded for application across the Bear Creek Riparian Corridor. Maps are being created showing the desired concepts. DMAs, the RM, and partners will use the maps to evaluate what the desired conditions are in areas of interest, look at what they currently are, and develop specific strategies/prescriptions and funding requests to help us achieve those desired conditions. The RM is also the lead in creating maps for the work being completed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025