## Education and Outreach
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter or other publication(s). Regional program will continue to promote and share TMDL topics on the Stream Smart website. The regional program will also provide general content for use on websites, in newsletters, etc. | Staff, RVCOG, Partners | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Articles, social media posts, and interviews are completed throughout the year on various topics related to the TMDL, Stream Smart, and Phase II programs. Posts, blogs, and articles are distributed through local media, the Stream Smart Program including its social media platforms, on DMA's Websites, through partners, and the TMDL pages on RVCOG's website. Articles and interviews have featured the Water Quality Press Release/Monitoring, Creek and River Clean-ups, Restoration, Salmon Watch, Volunteer Opportunities, and other activities. Examples are included in the Articles and Blogs tab, and the Stream Smart Posting Examples. Additional information can be found on https://www.stream-smart.com/recent-posts/. Copies of the materials referenced in this report can also be found on the Bear Creek TMDL Page (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/) | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics. Regional information will be updated on RVCOG's TMDL pages and the Stream Smart TMDL related pages as part of the regional TMDL participation. | Staff time, RVCOG | DMA’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | The Stream Smart website is updated monthly (or more frequently as needed) with new content, links, blogs, and events. Many of the education and volunteer activities that are part of the implementation programs form DMAs and/or MS4s are located on Stream Smart. In addition to updates, the RM and/or contractor(s) update the pages, checks for broken links, and other service related tasks needed to keep the site up and running. The RM also hosts TMDL related websites on RVCOG's website are updated quarterly or more frequently as needed. There are general TMDL pages for the Bear Creek TMDL The Rogue Basin TMDL, and the City of Jacksonville. There is also information and links to other related programs including BCRI, restoration maps, reporting, and other information. There are also cross links to and from DMA websites on the Stream Smart website as the DMAs (and MS4s) are major supporters of the program. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Examples of program that meet the TMDL goals that are done in partnership with other programs (NPDES Phase II) or just for the TMDL program include Salmon Watch, participation in local events (the Salmon Festival, Earth Day, Bear Creek Fall Festival), regional programs (Jackson SWCD Field Camp), programs with schools, partnerships with other groups, volunteer plantings, the August Institute, and other programs. | Continue to support the Regional Programs by working with RVCOG. | Workshop/Program participation and measurable results (number of projects completed, participants, etc.). | Annually | Annual Action Plan and Subsequent Report. | Events have rebounded in terms of attendance post COVID and wildfires. Most of the programs covered in this table were conducted under the Stream Smart Program or Stream Smart was a key partner and coordinator. A full season of Salmon Watch was conducted in the Fall of 2023, with an additional hybrid program (Salmon Watch and Eggs-to-Fry Program release) held in December, and two days of a Spring Program in April of 2024 with Talent Middle School. Overall, through those programs, we completed 35 in person field days with 30 different schools. In addition, we worked with 20 different partners including DMAs. The Fall Bear Creek Clean-up (September 2023) had 114 participants and picked up 4,895 lbs of trash and removed invasive species (estimated 0.5 acre). Statistics for the Spring clean-up were not available at the time of reporting with the exception of Pine Street in Central Point which had 52 volunteers, several clean-up location, planting (20 trees and shrubs), and maintenance of sites. In addition, there were 11 other volunteer activities volunteer events that were supported by the Stream Smart, the TMDL and Stormwater Programs had 173 attendees. Other events for the season included the Southern Oregon Regional Envirothon, staffing a booth and Ecoquest Activity as part of the Rogue Valley Earth Day, staffing booths at 2 other Earth Day Events, tabling for the Change For Good Program, work with the Jackson County Library District on the Salmon Watch Traveling Road Show, conducting regular activities as part of the Adopt-A-Greenway, Adopt-A-Street, and Adopt-A-River Program (Stream Smart Sections), working with Oregon State University's Student Watershed Assessment Team (SWAT), hosting events for the Move for Your Water, continuing to work with a Crater Renaissance Academy on activities on the Adopt-A-Greenway Section and serving on the Crater Renaissance Academy's Careers in Technical Education Board. Events and other activities reached more than 750 community members. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns including promoting and using the program for relevant programs, sharing posts from online media, and submitting content as appropriate for social media use. | Staff time & support funding. | DMA’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report. | The TMDL DMAs provide direct funding for the Stream Smart Program in conjunction with Phase II Programs and partners. As a result, there is overlap in program implementation and in subsequent reporting with many activities meeting the needs of both programs. The TMDL portion focuses on the dry weather portion of the TMDL and serves as the only participation for communities that don't have separate MS4 programs. Medford, Ashland, Jackson County, and Central Point participate as members of the Advisory Committee. In addition, Grants Pass and Josephine County also serve on the committee with the RM. Examples of Stream Smart activities conducted during the reporting year can be found in the Stream Smart tab. Funding provided by the DMAs and MS4s support the website (domain name registration, hosting, tracking, updates, contracted services for updates, content updates and addition (RM), event postings). In addition, the funding supports all related activities including marketing, postings, articles, meeting coordination, program promotion, development of materials (e.g. signs), and events and activities. In addition, DMAs participate in activities (e.g., instructing modules for Salmon Watch, participate in Clean-ups), have links to and from Stream Smart on their website, and use materials (logos, articles, posts) through the year as appropriate. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Provide outreach and technical support focused on riparian restoration activities. Includes tie in with the Stream Smart program, local assistance programs (Jackson SWCD), and the regional riparian program (Planting Plan including plant recommendations, site selection, invasive species recommendations). | Continued participation in the regional program. | Continued distribution of outreach materials, providing technical assistance to landowners, schools, and other groups. Providing continued support for assistance programs (e.g., SWCD riparian program). | Annually | Summary of activities and materials provided. | Planting sites are identified, mapped, and documented using Survey 1-2-3, Google Earth, and ArcGIS online. With the Almeda and Table Rock fires, the fire footprint areas were identified as the primary areas needing restoration. There are some areas that were not impacted by the fire that are also being evaluated and prioritized for planting. Areas are identified by the RM, DMAs, BCRI member, and partners. Local prioritization pre-fire focused on the sites identified in the Bear Creek Restoration Initiative Restoration Plan. Information on the sites is on the BCRI information page (https://rvcog.org/bear-creek-restoration-initiative/). Post-fire, restoration is being directed and prioritized by the Bear Creek Natural Resources Plan, BCRI efforts, Envision Bear Creek, and funding that was received post fire for recovery and rehabilitation. In addition, as part of the prioritization of projects and updating BCRI plan, a workshop was held to identify additional projects in June. Projects were submitted by or on behalf of Central Point, Phoenix, and Medford. In addition, the RM provides direct information and technical assistance at meetings, workshops, through phone calls, and other venues. Planting guidance and instruction is provided at all of the planting events. Topics included species selection, how to plant, goals of the planting (water quality protection, fish and wildlife habitat, managing fire risk and public safety, etc.). In addition, the RM serves as a point of contact for questions and refers partners, municipalities, schools, and the public to the appropriate entity, or resource (e.g., SWCD riparian rebate program when active), or the RM will provide technical assistance directly. Lists af activities are detailed in the activity summary tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time – potential coordination with RVCOG and local groups | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | The RM continues to work with both local and regional groups on educational and outreach programs. In 2023-2024, a portion of the restoration work and outreach was combined with the efforts of the Bear Creek Restoration Initiative. The RM worked as part of the BCRI Restoration and Stakeholder Engagement Working Groups tp promote the work of BCRI and the Bear Creek Natural Resources Plan. The work led to the Bear Creek Summit in November 2023 which was attended by over 60 people and the RM was a speaker and the Bear Creek Restoration Workshop in June 2024 (20 attendees). At the June workshop, the RM worked on refining regional maps using an ESRI based platform and creating an electronic version of the intake form using Survey 1-2-3 to facilitate mapping efforts and also allow for field documentation of sites (https://arcg.is/00Ly8X1). We are also fostering new partnerships and opportunities to tie in other programs (e.g., drinking water and the Rogue Drinking Water Partnership). In 2024, we hosted an activity Make a Move For You Water which focused on combining the event with a restoration project in Stream Smart's Adopt-A-Greenway section. We also partnered with the Jackson County Library District for a summer program featuring a 1 hour version of the Salmon Watch Program "The Salmon Watch Traveling Road Show". The first class was held in June and attended by 12 people. Stream Smart has continued to focus more on social media activities than the website. In 2023-2024, we have 594 Facebook Followers and 250 Instagram Followers. Our Facebook reach was 15,000 and we had 1,4000 visits (an increase of 271% from last year). Instagram reach was 91 and we had 51 visits which was a 34% increase from previous year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. RVCOG will continue to collect stream samples monthly at sites throughout the region. | Continued participation in the regional monitoring program. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | The Regional Monitoring program continues to be a very successful part of the Regional TMDL Program. We collect over 350 samples annually from streams and storm drains (including the hot spot program). Data are analyzed overall and by season to look for patterns (see data analysis tab). In addition, we assign scores for the creeks annually based on exceedance data and creek a simple "score card" for the watershed for summer bacteria levels. We also look at the seasonal and annual patterns year to year to compare them to see if there are any long term patterns or trends. All water quality data is submitted to DEQ. TMDL implementation actions are also tracked on an ongoing basis by RVCOG electronically through the use of surveys, maps, and/ or spreadsheets. This tracking helps us to evaluate progress versus benchmarks. Specialized projects are also implemented to help look at specific concerns. In 2023-2024, monitoring data collected under an OWEB grant with in kind match provided by the TMDL monitoring program was analyzed and reporting was completed. Information on the fire monitoring project including reports can be found on (https://rvcog.org/almeda-fire-monitoring/) . | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG as requested | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | No separate reports were given to management by the RM at DMA Council or Commission Meetings. Updates on projects including the Stream Smart Program, and clean-ups were given at RVCOG Board Meetings which include representatives from City Councils and County Commissioners. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. Regional TMDL support also provides support for the TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | DMA staff attended quarterly meetings and provided updates during the roundtable updates. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ. RVCOG will track and report on regional activities. | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Completed with the submittal of this document and accompanying forms. Additional information including copies of the full supplemental materials (tabs) can be found online at https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025