## Bacteria Matrix
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Update inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time. RVCOG if needed. | Report on new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks with stations. Add a percentage of stations added until 100% of parks have stations. | The City deployed approximately 140,000 bags during this reporting year throughout our public parks system. All parks stations were established through previous implementation activities. No future stations are currently planned since the City feels there is adequate coverage. If a new station is planned or constructed, the location will be noted or mapped and added to the annual report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volumes (Post construction). | Continue to incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff through municipal codes and ordinances. | Staff Time, Work with RVCOG for tracking and funding support for projects (grants, partnerships) | Track the features installed, size and treatment expectations as they are installed by updating the LID map annually. | Ongoing as development occurs. | In Phase II report. Limited tracking and mapping completed by the Regional Manager (RVCOG) as requested. | The Regional electronic survey form is available to inventory and map features (https://arcg.is/1zbb5e) that was created for regional use and will inventory and map as requested. New data collected by the survey can be found in the Tracking Map and Survey tab. Most annual work is completed under local Phase II programs and included in their annual MS4 reports. All tracking and other information collected by the RC is included in the annual reports in the forms of updates. In addition, online maps show up to date tracking (https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=018eec42042b4216b7812956b974593f). No sites were inventoried by the RM in 2022-2023. The RC will work with the City to get sites added to the map and/or to link the map to the TMDL page. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide educational opportunities including hands-on activities, resources, articles in newsletters/publications, and/or promote local workshops. | Staff time, Work with RVCOG, Partners. | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Summarize overall activity including number of projects: number of downspouts disconnected, rain gardens constructed, and participants. | General information, workshops, volunteer opportunities, and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/), and information on the TMDL pages on RVCOGs website. One page is for the Rogue Basin page (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/569-2/) and one is for the City's page (https://rvcog.org/grants-pass-tmdl/). In the spring of 2023, the pledge feature of the Stream Smart website was update which allowed users to pledge to reduce their impervious surface area. Options for the pledge include disconnecting your downspout and letting flow into a rain garden (https://www.stream-smart.com/how-to-get-involved/pledge/impervious/). In addition, the Rain Garden Guide is available on the Stream Smart website (https://www.stream-smart.com/wp-content/uploads/2020/07/Rain-Garden-Guide.pdf), the Planting for Stormwater Quality brochure (https://www.stream-smart.com/wp-content/uploads/2023/02/Planting-For-Stormwater-Quality.pdf), and a link to the City of Grants Pass Stormwater Design Manual and the Regional Stormwater Design Manuals. | Year 1: July 2020-June 2020
Year 2: July 2021-June 2021
Year 3: July 2022-June 2022
Year 4: July 2023-June 2023
Year 5: July 2024-June 2024
|  | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RM during the implementation year. Most stormwater work for the City is completed by the City's Public Works Department under the Phase II program and included in their report. The RM will work with the DMAs as requested to evaluate potential funding for BMP implementation and apply for funding. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Municipal Operations | Implement Stormwater Management Practices as time and funding permits. Examples activities include: Good Housekeeping, fleet maintenance, street sweeping, and site control (erosion) to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. In Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). Part of Regional Monitoring Program. | Review and refine illicit discharge and hot spot water sampling program as needed. Participation in the regional TMDL programs addresses sampling of storm drains to evaluate their impact on TMDL pollutant levels, tracking and investigation of concerns as needed (or requested) especially related to TMDL concerns, and serving as a point of contact for water quality concerns. | Staff Time | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, Annual report or regional activities generated by RVCOG. | Addressed under the City's Phase II Program. The RC has a form to conduct visual inspections of storm drains (as part of Survey 1-2-3) and mapped on ArcGIS. The RC serves as a point of contact for regional water quality concerns. Contact made are documented and reported to the appropriate DMA, agency, or OERS. A contact list is updated and distributed annually to the DMAs and is also available online. The Stream Smart website also contains information on reporting spills and contains the contact sheets (shown in the contact sheet tab). In addition, the RC investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). Concerns and actions are also documented in the activity summary tab and presented at quarterly TMDL meetings (by the RM, DEQ, and other as part of the TMDL Roundtable/Updates). The RC followed up with the City regarding a sewer spill that was reported to OERS that might impact the City from Evans Creek. | Year 1: July 2020-June 2021
|  |  | Continued participation in regional program through RVCOG. |  |  |  |  | Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Part of phase II compliance. | Ongoing | Update on the number of investigations and any enforcement actions taken. Any activities tracked or responded to by RVCOG are including in the annual report of regional activities.. | The RC investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). The RC followed up with the City on a sewer spill upriver that was reported to OERS that would potentially impact the City. The RC also participates as part of the Rogue Drinking Water Partnership (RDWP) and reports on (and investigates) potential threats to source water areas. In 2022-2023 investigations and follow up by the RC have been upriver above the Medford Water Commission intake. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. This could be summarized in the NPDES Phase II program report if applicable. | Activity reported in the Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RC during the implementation year are reported to the appropriate DMA, MS4, and/or DEQ. Concerns and actions are also documented in the activity summary tab. The RC can collect samples and analyze them for the City or deliver them to the lab as requested. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time. RVCOG. Partners | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Erosion and pollutants from the Almeda and Central Point fire and Obenchain were identified in previous years as a continued concern, particularly in relation to the City's water intake and impact on their drinking water supply. For the Almeda fire, the RM, RVSS, and the BCRI continued to implement restoration projects to help stabilize the area and also kept up with visual monitoring of the area during field work and site visits. In addition, a comprehensive two year monitoring program is underway funded by OWEB to study the long term impacts of the fire and look at where restoration efforts need to be focused and on what parameters. Data collected includes comprehensive metals and nutrients, 6 PPD Quinone, diesel and other hydrocarbons, and HABS (summer 2022). For the Obenchain fire, Jackson Soil and Water Conservation District has been working with landowners to restore the are post fire to help with stabilization and water quality concerns. In addition, monitoring has been completed by the Medford Water Commission (MWC) looking at impacts to the Rogue and it's tributaries in the upper watershed. Through the RDWP, the City works with the RC, MWC, other drinking water providers, and partners on a number of drinking water related issues including developing communication amongst the partnership and emergency personnel for spills including sewage into the river and in developing a comprehensive response strategy for spills. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Temperature Matrix
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Protect riparian areas by implementing current riparian protection standards | Implement current ordinance or riparian buffer standards. | Staff Time | List of actions taken. | Ongoing | Annual reports will track number and type of actions taken. | The City, County, and partners (ODFW) worked on several actions related to riparian ordinances involving the removal of invasive species without a plan or a timely plan for restoration (per riparian ordinance) for replacement with native species. As a result of the actions, the RC worked with partners to complete two restoration projects one on Jones Creek and one the Rogue River that are detailed later in this report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for restoration projects. This is a regional task in collaboration with RVCOG and/or other local groups. | Line item established in budget with annual funding. | first year program development and discussion, with line item and funding pending annually thereafter if program is established | Planting statistics, leveraged funding (including in-kind), and/or projects. This portion focuses on the implementation of restoration projects and builds on the DMA wide restoration program. | No specific line item was established for restoration activities for this implementation cycle (5-year plan) as part of the regional program. The City contracts with the RM to work on restoration projects in the City and County and partner with organizations in both Jackson and Josephine County. Work was completed by the RC on multiple sites (2 planting and 4 sites for invasive species management) resulting in the planting of 400 willow cuttings and 250 other species, removal of 2 acres of invasive species, and $11,100 of funding (see stats and budget restoration tab). Partners on the planting projects included (in addition to the City and the RC): the Middle Rogue Steelheaders, ODFW, The Freshwater Trust (TFT), Applegate Partnership and Watershed Council (APWC), the Rogue River Watershed Council (RRWC), Stream Smart, Oregon Department of Forestry, community volunteers, and a local HOA. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. The regional program builds on the work completed in previous years and uses materials found in Bear Creek and Rogue Basin Planting Plans to prioritize and begin implementation. | Continue to participate in the regional program through RVCOG. | Completion and record of annual efforts (map updates, statistics, funding) | Annually | Provide updates on the status of sites in each DMA, new sites identified and prioritized, costs, schedule, and other logistics. Develop an annual goal for restoration (e.g., number of trees planted, miles restored, etc.). Outreach covered under the Education and Outreach Section. | The City contracts with the RM to work on restoration projects in the City and County and partner with organizations in both Jackson and Josephine County. Work was completed by the RC on multiple sites (2 planting and 4 sites for invasive species management)s resulting in the planting of 400 willow cuttings and 250 other species, removal of 2 acres of invasive species, and $11,100 of funding (see stats and budget restoration tab). In addition, the restoration map was updated for the City https://rvcog.maps.arcgis.com/apps/instant/nearby/index.html?appid=7b64357d6e364e9eb5fc7c5829b3f0a9&locale=en. Underlying data for the map is also updated as new sites are identified, work is completed, and new layers added. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Volunteer Planting Event(s) | City participates in events: Events may include at least one featured tree planting project or tree giveaways to residents. Events will be planned in the community, as part of an event (e.g. Fall Festival, Earth Day), incorporated into Salmon Watch (riparian section), and/or planned as a regional event. | Staff time. RVCOG. Partners. And/or volunteers. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | A minimum of one event held each year with local participants and activities that educate and implement tree planting. | Three volunteer events were held in Grants Pass involving restoration, invasive species removal, and/or and planting in addition to the Rogue River Clean-up which provided some removal of invasive species. One event was on a section of Jones Creek, one was on the Rogue River just upriver of the Pedestrian bridge, and one was on a section of Gilbert Creek. Partners on the project in addition to the RC and City included the Middle Rogue Steelheaders, ODFW, The Freshwater Trust (TFT), Applegate Partnership and Watershed Council (APWC), the Rogue River Watershed Council (RRWC), the CWMA, and a local HOA. 500 willows (donated by the APWC) were planted and 250 other species with plants donated by TFT (100 plants) or purchased by the City ($500.00). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publicly owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time. Regional participation with RVCOG. Partnerships with local groups. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify (map) Implemented projects on an annual basis until 100% complete. If all public lands are completed, maintain plantings and add any new areas that become public. | The RC has been working with the City to maintain a section of riparian area and a wetland area along the Rogue River in Reinhart Volunteer Park (RVP) just downstream of the pedestrian bridge. The RC developed a rough concept plan for the park (See concept plan tab). Identified projects (completed, in progress, or work needed) are mapped (https://rvcog.maps.arcgis.com/apps/instant/nearby/index.html?appid=7b64357d6e364e9eb5fc7c5829b3f0a9&locale=en). In addition, the RC and City have worked with the Cooperative Weed Management Association (CWMA), Stream Smart, and volunteer groups (e.g., Dutch Brothers) to collaborate with the Let's Pull Together Initiative and other clean up efforts. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Stormwater Runoff | Reduce warm stormwater runoff volumes (post construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from streets, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects that incorporated LID or other methods into development and redevelopment plans | The City of Grants Pass recently passed changes to the Municipal Code and Development Code that will mandate LID principles for future developments. The Development Code was passed in October and the new Stormwater Management Manual will be effective by the end of October. To date, no LID projects have been completed, but next year several are being planned. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals including identification of new invasive species of concern and control methods and new restoration techniques. | Staff time. Regional programs through RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The focus of adaptive management regionally is related to restoration has been in continued development of strategies for restoring riparian areas after fires (e.g., Almeda and Obenchain) including ongoing management of invasive species in the areas that burned and in between (areas that didn't that pose a high risk) including long term management. Much of the focus has been on the Bear Creek corrido, but the concepts being developed will be applicable to the Rogue River and its tributaries. Specifically, the restoration concepts that balance multiple needs of the corridor management and users, and in implementing these new strategies. The basis for the restoration concepts developed came from participation in the BCRI restoration group and as part of the technical team on a project with EPA (Wildfire Recovery Assistance for Oregon) that led to the completion of the Bear Creek Natural Resources Plan (https://www.stream-smart.com/wp-content/uploads/2023/05/Bear-Creek-Final-NRP-Compiled_04.14.23.pdf). The plan development included a workshop where we developed the initial restoration concepts that are in the plan. The RC participates in the restoration group for the Rogue Basin Partnership (RBP) which looks at issues outside of the Bear Creek corridor. One concept that is being explored is regional permits for restoration projects in both counties. Regional permits would allow for projects that follow the guidelines to be able to be implemented more efficiently and effectively through an expedited approval process. In addition, the RC is working with the CWMA to coordinate events with the Stream Smart program and regional TMDL activities (e.g. Let's Pull Together and Clean-ups, and the Adopt-A-River program). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Education and Outreach Matrix
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter or other publication(s). Regional program will continue to promote and share TMDL topics on the Stream Smart website. The regional program will also provide general content for use on websites, in newsletters, etc. | Staff, RVCOG, Partners | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Articles, social media posts, and interviews were completed throughout the year. Posts, blogs, and articles are distributed through local media, the Stream Smart Program including its social media platforms, on DMA's Websites, through partners, and the TMDL pages on RVCOG's website. Specifically, articles, interviews, and blogs have featured Stream Smart's volunteer programs (Bear Creek Clean-ups, Adopt-A-Greenway, and Rogue River Clean-up), the water quality press releases, riparian restoration, activities and events, and other topics. Blog posts can be found on the Stream Smart site at https://www.stream-smart.com/recent-posts/. Copies of materials referenced in this report can be found on the report link (long form) located on https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/. Articles related to the City include the Baker Park Floodplain Clean-up (https://www.stream-smart.com/a-village-came-together/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics. Regional information will be updated on RVCOG's TMDL pages and the Stream Smart TMDL related pages as part of the regional TMDL participation. | Staff time, RVCOG | DMA’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | The Stream Smart website is updated monthly (or more frequently as needed) with revisions, new content, links, events, blogs, and other information. There are cross links to and from DMA websites for most communities with the Stream Smart page. In addition to the web content, TMDL related information is also posted and shared on the social media. TMDL related websites hosted on RVCOG's website are updated quarterly or more frequently as needed. There are general TMDL pages for the Bear Creek TMDL, the Rogue Basin TMDL, and the City of Grants Pass. Examples of changes/updates to the websites include the re-establishment of the Pledge page on the Stream Smart website refer to link for the picking up after your pets pledge (https://www.stream-smart.com/how-to-get-involved/pledge/pet-waste/pet-pledge/), the creation of a dedicated blog page (https://www.stream-smart.com/recent-posts/), updated riparian (https://rvcog.maps.arcgis.com/apps/instant/nearby/index.html?appid=7b64357d6e364e9eb5fc7c5829b3f0a9&locale=en) and TMDL tracking maps (https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=adbb31b9ef8d4e8690bef7392edd1349), and updating the Stream Smart resource page to include the Bear Creek Natural Resources Plan and links to the City's and Regional Stormwater Design Manual. In addition, quarterly TMDL reports and other meeting information was uploaded to the City's TMDL website (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Examples of program that meet the TMDL goals that are done in partnership with other programs (NPDES Phase II) or just for the TMDL program include Salmon Watch, participation in local events (the Salmon Festival, Earth Day, Bear Creek Fall Festival), regional programs (Jackson SWCD Field Camp), programs with schools, partnerships with other groups, volunteer plantings, the August Institute, and other programs. | Continue to support the Regional Programs by working with RVCOG. | Workshop/Program participation and measurable results (number of projects completed, participants, etc.). | Annually | Annual Action Plan and Subsequent Report. | Events are starting to return to pre-COVID levels in terms of opportunities for participation. A full Salmon Watch Program was conducted in the Fall of 2022 with an additional hybrid class conducted with the Oregon Department of Fish and Wildlife's Salmon Fry Release Program in December. Overall, the program reached over 1,260 students over 28 field days. The Rogue River Clean-up and Let's Pull Together event had 155 participants and picked up 10 cubic yards of trash and removed 32 acres of invasive species. In addition, there were several volunteer activities conducted as part of the Stream Smart Volunteer Program supported by the TMDL and Stormwater Programs had 153 attendees which included work in the City (2 restoration projects, Adopt-A-River Clean-ups, Weed Pull, and Clean-ups). Other events for the season included the Southern Oregon Regional Envirothon, staffing a booth and Ecoquest Activity as part of the Rogue Valley Earth Day, conducting regular activities as part of the Adopt-A-River, working with Oregon State University's Student Watershed Assessment Team (SWAT) on fire restoration projects, and hosting events for the Worldwide Walk for Water. Events and other activities reached over 500 more community members. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns including promoting and using the program for relevant programs, sharing posts from online media, and submitting content as appropriate for social media use. | Staff time & support funding. | DMA’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report. | The TMDL DMAs provide direct funding for the Stream Smart Program in conjunction with Phase II Programs and a few partners. As a result, there is overlap in program implementation and in subsequent reporting. The TMDL portion focuses on the dry weather portion of the TMDL and serves as the only participation for communities that don't have separate MS4 programs. Medford, Ashland, Jackson County, and Central Point participate as members of the Advisory Committee. In addition, Grants Pass, Josephine County, and Medford Water Commission also serve on the committee with the RC. Examples of Stream Smart activities conducted during the reporting year can be found in the Stream Smart tab. Funding provided by the DMAs and MS4s support the website (domain name registration, hosting, tracking, updates, contracted services for updates, content updates and addition (RM), event postings). In addition, the funding supports all related activities including marketing, postings, articles, meeting coordination, program promotion, development of materials (e.g. signs), and events and activities. In addition, DMAs participate in activities (e.g., Salmon Watch), have links to Salmon Watch on their website, and use materials (logos, articles, posts) through the year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Provide outreach and technical support focused on riparian restoration activities. Includes tie in with the Stream Smart program, local assistance programs (Jackson SWCD), and the regional riparian program (Planting Plan including plant recommendations, site selection, invasive species recommendations). | Continued participation in the regional program. | Continued distribution of outreach materials, providing technical assistance to landowners, schools, and other groups. Providing continued support for assistance programs (e.g., SWCD riparian program). | Annually | Summary of activities and materials provided. | Planting sites are identified, mapped, and documented using Survey 1-2-3 and ArcGIS online. With the Almeda and Table Rock fires, the fire footprint areas were identified as the primary areas needing restoration from a regional perspective. There are also some areas that were not impacted by the fire that are also being evaluated and prioritized for planting. Areas are identified by the RM, DMAs, and partners. Local prioritization pre fire focused on the sites identified in the Bear Creek Restoration Initiative Restoration Plan. Information on the sites is on the BCRI information page (https://rvcog.org/bear-creek-restoration-initiative/) including a link to the Final Report at the bottom of the page in the Products section. The BCRI plan is being updated to reflect priorities after the fires, work that has been completed, and research that should be completed in the early 2022-2023 implementation year. In Grants Pass and Josephine County, the RC works with the City, partners, and the public to identify, prioritize, fund, and implement projects. In addition, the RC provides direct information and technical assistance at meetings, workshops, through phone calls, and other venues. Planting guidance and instruction was provided at all of the planting events including the Jones Creek and Rogue River planting. Topics included species selection, how to plant, goals of the planting (water quality protection, fish and wildlife habitat, managing fire risk and public safety, etc.). In addition, the RC serves as a point of contact for questions and refers partners, municipalities, schools, and the public to the appropriate entity, or resources or the RC will provide technical assistance directly. Lists at activities are detailed in the activity summary tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time – potential coordination with RVCOG and local groups | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | The RC continues to work with both local, statewide, and regional groups on education and outreach programs. Most of the outreach completed for the City's TMDL program is through the Stream Smart Program (https://www.stream-smart.com). The Stream Smart Program is also expanding their volunteer programs by continuing with the Adopt-A-Greenway Program and adding the Adopt-A-River (Rogue River near Hog Creek) this implementation year. In addition, the RC is partnering with the CWMA and local groups to increase the number of events offered during the year and increase the participation in the City and County volunteer programs and events. The RC will also host a meeting or series of meeting to look at expanding the Rogue River Clean-up to include Gold Hill and/or Rogue River. Stream Smart has also switched to focus more on social media activities than the website since most of the use in 2022-2023 was to the social media channels - a reach of over 24,000 based on of Facebook (23,875) and Instagram (1,209) when compared to the website 2,642 users. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. RVCOG will continue to collect stream samples monthly at sites throughout the region. | Continued participation in the regional monitoring program. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | TMDL implementation actions are tracked on an ongoing basis by RVCOG electronically through the use of surveys, maps, and/ or spreadsheets. In addition, data has been collected by the City as part of the Rogue Drinking Water Partnership to look at the impacts of the local fires (Almeda, Table Rock, and Obenchain) on the Rogue River and potential treatment and drinking water concerns. Data collected as part of this program is being evaluated for the TMDL program. The City and the RC are looking for support to develop and implement a monitoring program to help evaluate conditions in the City's waterways and to help evaluate if (and how) implementation is improving water quality conditions. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG as requested | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | No separate reports were given to management by the RM at DMA Council or Commission Meetings. Updates on projects including Clean-ups were given at RVCOG Board Meetings which include representatives from City Councils and County Commissioners. In addition, a workshop with the City Council to discuss the Reinhart Volunteer Project is planned in the 1st quarter of the implementation year for 2023-2024. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. Regional TMDL support also provides support for the TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | DMA staff attended quarterly meetings and provided updates during the roundtable updates as needed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ. RVCOG will track and report on regional activities. | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Completed with the submittal of this document and accompanying forms. Additional information including copies of the full supplemental materials (tabs) can be found online at https://rvcog.org/grants-pass-tmdl/. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025