## DEQ Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Develop an inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time | Track number of existing stations and report new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks/public areas with stations. Add a percentage of stations added until 100% of parks/public areas that need stations have stations. | The City deployed approximately 100,000 bags during this reporting year throughout our public parks system. All parks have stations established through previous implementation activities. There are currently 23 stations and no stations are currently planned. If a new station is planned or constructed it's location will be noted or mapped and added to the annual report. | Year 1: July 2020-June 2021:
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volume (Post Construction). | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track the features installed, size and treatment expectations as they are installed. | Ongoing as development occurs. | This strategy is tied into the Phase II program and dependent on funding availability to design and construct capital improvements, as well as on private investment in new or redevelopment projects. Report out on features being installed and maintained in capital projects that incorporate these. | All large capital road improvement projects in the City now implement LID stormwater improvements. While not currently required in the City, the City does them in recognition of the pending Stormwater Management Manual adoption which will require them following adoption. A recent example was the Willow Lane Improvements Project. Several other projects are being designed for future years with similar LID system such as the Hillcrest Drive Improvement Project and the Allen Creek Road Improvements Project. The RC created an electronic survey form that can be used to inventory and map features (https://arcg.is/1Xe10i0). All tracking and other information collected is included in the City's stormwater program and included in the annual reports. No active tracking was completed by the RC in 2022-2023. | Year 1: July 2020-June 2021:
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education through design workshops, volunteer opportunities, and/or other methods. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Part of phase II program. Annual update on program development and relevant statistics in Phase II report. | General information, workshops, volunteer opportunities, resources (e.g., the OSU rain garden guide), and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/), and on the City's TMDL page on RVCOGs website (https://rvcog.org/grants-pass-tmdl/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Address water quality impacts of stormwater | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RC during the implementation year. The OWEB small grant program does feature a category for Urban Impact Reduction which could be used to fund BMPs. The RC will work with the City to evaluate potential funding for BMP implementation. Use of rehabilitated brownfield sites as stormwater BMP/LID locations was considered as part of the Coalition Community Wide Assessment Program that ended in early 2022. Grants Pass was a member of the Coalition. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Pollution Prevention/Good Housekeeping - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage, sediment controls, street sweeping to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken in NPDES Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. More information can be found in the MS4 Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). | Review and refine illicit discharge and hot spot water sampling program as needed | Staff Time. RVCOG | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, | The RC serves a point of contact for regional water quality concerns. Calls that are received for Grants Pass and other jurisdictions are documented and referred to the appropriate entity, agency, or response including OERS, In addition, hot spot contact information including lists are available online through the Stream Smart program and in other locations and are updated annually. The hot spot monitoring form is also used to record and document occurrences reported (https://arcg.is/1byiCy). More information can be found in the MS4 Phase II report and in the activity summary that is included as part of this report. No reports were received by the RC during the implementation year. Additionally, City staff began monitoring outfalls for temperature and other parameters as part of the MS4 requirements. These initial readings will serve as a baseline for future monitoring to detect potential illicit discharges. In addition, program results will be used in the hot spot monitoring program (e.g., when the City records a result that is of concern (red flag) or observes something during the monitoring, the City will follow up and investigate as needed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Annual update on actions taken in NPDES Phase II report. | As part of the IDDE program, the RC is available as directed by the City to conduct visual inspections of storm drains and areas of concern and document what is found. In addition, the RC can collect samples to see what the impact is on TMDL parameters. All activity is documented in the matrix. More information can be found in the MS4 Phase II report. No calls were received by the RC or City this year. Additionally, City staff began monitoring outfalls for temperature and other parameters as part of the MS4 requirements. These initial readings will serve as a baseline for future monitoring to detect potential illicit discharges. In addition, program results will be used in the hot spot monitoring program (e.g., when the City records a result that is of concern (red flag) or observes something during the monitoring, the City will follow up and investigate as needed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Annual update on actions taken in NPDES Phase II report. | Any activity will be included in the Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time. RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RC during the implementation year are reported to the City and/or DEQ. No concerns were reported this year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. | Staff time. RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The RC is working with a number of partners to develop a Watershed Report Card for the Rogue Basin which would include bacteria data in and around Grants Pass. The goal of the report card is to provide a tool to help with outreach to the public and tie into Stream Smart and other programs. Limited data exists in Grants Pass. The RC attends the Quarterly Stormwater Advisory Team (SWAT) Meetings and reports on activities related to Stream Smart and TMDL programs in both Counties. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Temp
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Implement current riparian buffer standards/riparian ordinance | Review site and land division proposals to ensure consistent buffers. Implement and enforce riparian ordinance | Staff Time | List of riparian buffer standards or riparian ordinance actions taken. | Ongoing | Annual reports will track buffer standards or riparian ordinance actions taken. | No activity/actions taken this implementation year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Incentivize new land division proposals to reserve floodplains as a natural open space | Review site and land division proposals for opportunities | Staff time | Program development. Keep records of protected areas. | Ongoing | Annual reports and 5-year reviews will track progress including number of projects, acres preserved/restored, and establish recommendations for improvements as needed. | No activity/actions taken this implementation year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for implementation of projects (active management of invasives, planting, etc.). RVCOG. Contractor(s), partners. | Line item established in budget with annual funding. | first year with line item and funding; annually thereafter | Budget development and reporting will demonstrate progress. Number of plantings or projects. | RC has been working with the City for developing and implementing riparian restoration programs and remove invasive species. Support for riparian species restoration and invasive species removal projects are included in the contract with RVCOG. New sites for restoration are identified, surveyed, and mapped during several field visits in the City. In addition, the RC works with the local CWMA, local organizations (e.g., RCC, Dutch Brothers, RBP, RRWC, TFT, local schools, and others) to develop and implement restoration and invasive species management projects. For example, we worked with the County Weed Management Agency to identify and implement projects for invasive species removal at Reinhart Park and as part of the Rogue River Clean-up. English Ivy, blackberry, starthistle, and other species were removed (3.3 acres). A copy of the City's map which is updated on an ongoing basis can be found at https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=d6088f0445664369953396d6db5880ae. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. | Staff time, RVCOG, partners. | Completion and record of annual efforts | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | No new sites were identified or catalogued during the implementation year. The implementation schedule for 2022-2023 has RC time scheduled for field work focused on the identification of sites needing restoration, invasive species management, and pollinator habitat. The City and RC continue to participate in regional programs with partners that focus on wider scale restoration activities including the Bear Creek Restoration Initiative (BCRI), and the Rogue Basin Restoration Working Group. The RC has continued to work with partners and volunteers to move previously identified projects from the planning to the active phase. Specifically the projects related to invasive species removal (e.g., Reinhardt Park). Most of the focus in 2021-2022 has continued to be been on fire restoration from the Almeda, Table Rock, and Obenchain Fires. Lessons learned including restoration and stabilization strategies following fires and building fire resiliency are being added to local restoration programs. In addition, the BCRI partners have been working to increase pollinator habitat, refine prioritization strategies, and evaluate (and test) options for long term management of restoration areas. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City participates in events: Events include at least one featured tree planting project, tree giveaways to residents, or restoration project activity (monitoring, maintenance, watering, invasive species management). | Staff time, RVCOG, partners. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | Events held each year with local participants and activities that educate and implement tree planting. | The City and RC participated in one event focused on invasive species management. An estimated 3.3 acres of invasives were removed by 35 volunteers as part of the Let's Pull Together Program. Restoring the sites with natives is being evaluated for future implementation years. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publically owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time, RVCOG, partners. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify Implemented projects on an annual basis | No new sites were identified or catalogued using Survey 1-2-3. The City and RC continue to participate in regional programs with partners that focus on wider scale restoration activities including the Bear Creek Restoration Initiative (BCRI), and the Rogue Basin Restoration Working Group. The RC has continued to work with partners and volunteers to move previously identified projects from the planning to the active phase. Specifically the projects related to invasive species removal (e.g., Reinhardt Park). The City is evaluating options for funding including applying for individual grants or participating in larger restoration programs that will include several projects and target larger funding sources. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Reduce warm stormwater runoff volumes (Post Construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from stormwater utility fund, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects (mostly vegetative buffer strips and such associated with new road projects) that incorporated LID or other methods into development and redevelopment plans. | Any activity will be included in the MS4 report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Riparian restoration strategies are being evaluated and modified in the region following the area fires in Jackson and Josephine County. As part of these strategies, initial stabilization protocols following areas being burned are being finalized. In addition, planning for increased fire resiliency, pollinator habitat, use of native regeneration as an active management strategy, and drought conditions including a lack of water for restoration are also being considered as part of current restoration planning. All changes in restoration strategies have the potential to impact the goals of the Temperature TMDL program. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Ed and Outreach
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter and/or other publications. | Staff. RVCOG. Partners. | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Articles, social media posts, and interviews were conducted throughout the year on various topics through the Stream Smart Program, the City's Website, and the City's TMDL page on RVCOG's website. Articles and interviews have featured Stream Smart's adopting of the section of the Bear Creek Greenway, the Rogue River Clean-up and other activities, Example articles are in the Articles tab in the full matrix available on the City's TMDL information page hosted by RVCOG (https://rvcog.org/grants-pass-tmdl/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics | Staff time, RVCOG | City’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | The Stream Smart website is updated monthly with new content, links and events (https://www.stream-smart.com). An advisory committee (AC) for the Stream Smart Program meets quarterly and discusses proposed changes to the website and reviews recent changes. Grants Pass serves as an active member of the AC. The GP TMDL page hosted on RVCOG's website is updated quarterly and more frequently as needed (https://rvcog.org/grants-pass-tmdl/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Example: Rain Garden, downspout disconnects, demonstration workshops, Salmon Watch Program, don’t feed wildlife etc. | Continue to support the Regional Programs by working with RVCOG. Additional Grants Pass specific programs will be conducted by City Staff, RVCOG, and/or volunteers. | Workshop/Program participation and measurable results (i.e. number of rain gardens installed, downspouts disconnected, number of students participating in Salmon Watch, etc.) | Annually | Annual Action Plan and Subsequent Report | Due to the ongoing impacts of COVID19, events, workshops, and volunteer activities were extremely limited in the first half of the year. Salmon Watch was an exception and was able to be fully conducted in the fall with a few additional classes held in the Spring. 31 field days were held with over 1,300 students. The Rogue River Clean-up was another big success story for the year and had 109 participants and picked up 20 cubic yards of trash. The Clean-up was also paired with the Let's Pull Together Weed Pull and removed invasive species (estimated 3.3 acres). Species removed included dyer's woad, yellow star thistle, spotted knapweed, and scotch brome. Participant levels were back up to pre-covid levels. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns | Staff time & support funding. | City’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report | The City of Grants Pass provides direct funding for the Stream Smart Program and participates as a member of the Advisory Committee. An example of Stream Smart activities can be found in the Stream Smart tab. In addition, the logo and social media platforms (Facebook and Instagram) are used to promote the City's programs including the Rogue River Clean-ups. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Participate in a basin-wide riparian restoration program and provide outreach to target areas. | Staff time. RVCOG. Other DMAs. Partners. Volunteers | Focus is on identifying, prioritizing, and moving toward implementation of projects | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | Any new sites identified are documented using Survey 1-2-3 and other methods. Planting and restoration strategies that are used in restoration by the City follow recommendations found in the Bear Creek and Rogue Basin Planting Plan. Updates and changes to strategies follow recommendation completed by the Bear Creek Restoration Initiative and other groups. The RC has also actively coordinate with local and regional groups (e.g., RRWC, TFT, CWMA, and others) in looking at opportunities for restoration in the Grants Pass area streams and the Rogue River. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | The City has participated in meetings developing new technologies particularly in the form of electronic data collection forms for TMDL and stormwater using Survey 1-2-3 and online mapping. Funding provided by the City supported the creation of the forms, data collection, story maps, and online mapping activities. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. | Staff time. RVCOG. Partners. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | TMDL implementation actions are tracked on an ongoing basis by RVCOG electronically through the use of surveys, maps, and/ or spreadsheets. In addition, data collected by the City as part of the Rogue Drinking Water Partnership to look at the impacts of the local fires (Almeda, Table Rock, and Obenchain) on the Rogue River and potential treatment and drinking water concerns is currently being evaluated as part of the Almeda Fire Monitoring Project. In addition, the City participates on the Almeda Fire Monitoring Technical Team which is studying the impacts of urban fires. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | No reports were given to management by the RC. The RC does update the RVCOG Board periodically on TMDL related activities (e.g., Clean-ups for 2021-2022). A representative from the Grants Pass City Council is on the RVCOG | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | Staff attended quarterly meetings and provided periodic updates during the roundtable updates as needed | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Completed with the submittal of this document and accompanying forms. In addition, the City provides links to the annual reports through their TMDL page on RVCOG's website. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Activity Summary
Summary Information |  |  |  | Statistics/Tracking Variables
General Statistics | [9 empty] | Program |  |  | Restoration Statistics |  | Brochure Details | [19 empty] | Meeting Attendance
Date | Event/Activity | Time and Location (if needed) | Description | Number of People | Number of Samples Collected | Number of Items Distributed | Funds Requested | Funding Leveraged, match, requested | Funded? | TMDL | Phase II | Both | Acres Restored and/or Number of Trees Planted | Acres of Invasives Treated | New Stormwater | SWEG | Stream Jack Co | Yard Care | SW | EPSC | Painting | Concrete | Salmon | Stream Smart stickers | Poop Pledge | Native Pledge | Stormwater/LID pledge | Pesticides Pledge | Salmon Stickers/tattoos | Stream Smart Poop Dispensers | Rain Garden Guide | NOAA Stickers | Streams JoCo | Other/notes | Medford | Ashland | Jackson County | Jacksonville | Phoenix | Talent | Central Point | RRVID | TID | MID | DEQ | ODF | SWCD | RVSS | RRK | RRWC | RBP | Grants Pass | Eagle Point | Josephine County | Curry County | Gold Beach | Rogue River | Eagle Point Irrigation District | Shady Cove | Gold Hill Irrigation District | Gold Hill | Jackson County | Cave Junction | Others
2021-07-01 | Salmon Watch Funding Application to JSWCD |  | Funding request for $5,500.00 for Salmon Watch support including supplies, contracted instructors, and transportation. Funding request approved on Thursday 7/22/21
2021-07-07 | Bear Creek Restoration Initiative (BCRI) Meeting | 2:00 pm - 4:00 pm
2021-07-21 | TMDL Quarterly Meeting | 1:00 pm to 3:00 pm | [7 empty] | X | [24 empty] | X | NO | X | X | NO | NO | X | [10 empty] | X | X | X | NO | NO | X | NO | NO | NO | X | X | NO | bar: RRVID to RBP
2021-07-27 | Salmon Watch Meeting with RVSS | 10:00 am to 11:00 am
2021-07-30 | Stream Smart Web Visitation |  | 105 | 105
2021-08-03 | Post-Fire WQ Monitoring Meeting | 1:00 pm - 2:00 pm
2021-08-04 | Rogue Drinking Water Parternship (RDWP) Meeting (Rogue River) | 10:00 am - 12:00 pm | Presented on SWAs, Watershed Patrol, and the NWQI.
2021-08-27 | Salmon Watch Meeting with RVSS | 10:00
2021-08-31 | Stream Smart Web Visitation |  | 134 | 134
2021-09-07 | Post-Fire WQ Monitoring Meeting | 1:00 pm - 2:00 pm | Discussed the status of the OWEB grant.
2021-09-08 | Meeting with Kara Baylog from OSU Extenstion | 13:00 | Talked about SWAT (student watershed assessment teams) monitoring in several fire area locations and surveying the BMPs for their effectiveness.
2021-09-14 | Salmon Watch Instructor Training | 8:30 am - 12:00 pm |  | 21
2021-09-15 | Stream Smart Quarterly Meeting | 9:00
2021-09-16 | Salmon Watch Instructor Training | 8:30 am - 12:00 pm |  | 15
2021-09-21 | Salmon Watch at McGregor Park | 9:30 am - 1:30 pm |  | 25-30
2021-09-21 | Post-Fire WQ Monitoring Meeting | 1:00 pm - 2:00 pm | Discussed the OWEB grant: QAPPs/SAPPs - contract out? Or done by the project manager? Can we adopt some before the next flush event? Use QAPPs sent by Amy Patton to Jennie Morgan, collect samples and hold until the end of October, and then bill (once the funding is available). Add those protocols in for the QAPPs for the project. Questions for Greg to ask: Can the lab analyze the samples but not bill until the start of the grant? 0.25 inches for the next flush, and 0.5 inches for the wet weather event.
2021-09-28 | Post-Fire WQ Monitoring Meeting | 1:00 pm - 2:00 pm
2021-09-30 | Stream Smart Web visitation |  | 144 | 144
2021-10-05 | Almeda Fire Monitoring Grant Check in Meeting
2021-10-12 | Almeda Fire Monitoring Grant Check in Meeting
2021-10-14 | RBP Board Meeting
2021-10-19 | Almeda Fire Monitoring Grant Check in Meeting
2021-10-19 | Salmon Watch at Scenic (CT - Salmon)
2021-10-20 | Salmon Watch at Scenic (CT - Salmon)
2021-10-20 | TMDL Quarterly Meeting
2021-10-21 | Salmon Watch at Scenic (Amie - Riparian)
2021-10-22 | Salmon Watch at Scenic (Greg - Riparian)
2021-10-22 | SWAT Meeting
2021-10-26 | Almeda Fire Monitoring Grant Check in Meeting
2021-10-31 | Stream Smart Visitors |  | 139
2021-11-02 | OWEB Monitoring Meeting
2021-11-03 | Salmon Watch at Touvelle (Greg - Lead. Riparian)
2021-11-04 | Salmon Watch at Touvelle (Greg - Lead. Macros)
2021-11-09 | OWEB Almeda Fire Monitoring Storm Drain Run
2021-11-09 | OWEB Monitoring Meeting - Mark G attended
2021-11-10 | Quarterly TMDL Meeting
2021-11-16 | OWEB Monitoring Meeting
2021-11-17 | RBP Monitoring Meeting
November | Stream Smart web visitation |  | 89
December | Stream Smart web visitation |  | 96
12/7, 12/14, 12/21, and 12/28 | OWEB Monitoring Technical Team Meetings
2021-12-08 | RDWP Quarterly Meeting
2021-12-09 | RBP Board Meeting
2021-12-15 | Stream Smart Meeting
1/4, 1/11, 1/18, and 1/25 | OWEB Technical Team Monitoring Meetings
January 5th | BCRI Monthly Meeting
January 5th | Senator Golden Water Forum |  | 100
2022-01-11 | RBP Riparian Working Group
2022-01-13 | Willamette Partnership Coordination Meeting
2022-01-19 | TMDL Meeting | 1-3 pm
2022-02-10 | Project coordination meeting with RRWC
2022-02-10 | Coordination meeting with RBP
2022-03-02 | Southern Oregon Regional Environmental Education Leaders (SOREEL) Meeting | 9-10:30 am | Quarterly check in with local education partners.
2022-03-03 | RDWP Quarterly Meeting
2022-03-16 | Stream Smart Quarterly Meeting
2022-04-04 | Rogue Valley Envirothon
2022-04-05 | Oregon Life Long Learning Institute (OLLI) Class - Restoration |  |  | 12
2022-04-12 | OLLI Class - Volunteer and Education Programs
2022-04-14 | Salmon Watch at McGregor Park |  | Pinehurst School | 12
2022-04-19 | OLLI Class - Clean Water Act Programs - TMDL and Stormwater
2022-04-20 | TMDL Quarterly Meeting
2022-04-22 | Rogue Valley Earth Day at SOU
2022-04-28 | Salmon Watch at TouVelle with McGloughlin Middle School
2022-06-15 | Stream Smart Quarterly Meeting
2022-06-16 | RBP Meeting - Presentation on BCRI
2022-06-28 | Jackson Soil and Water Conservation Day Camp |  | Taught the Macro-invertebrate and combined Water Quality and Riparian Salmon Watch Modules at North Mountain Park in Ashland
2022-06-30 | Rogue Drinking Water Parternship (RDWP) Meeting (Rogue River)
2022-06-30 | BCRI Stakeholder Engagement Meeting