## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Develop an inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time | Track number of existing stations and report new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks/public areas with stations. Add a percentage of stations added until 100% of parks/public areas that need stations have stations. | The City deployed approximately 100,000 bags during this reporting year throughout our public parks system annually. All parks have stations established through previous implementation activities and no new ones are currently planned. If a new station is planned or constructed it's location will be noted or mapped and added to the annual report. | Year 1: July 2020-June 2021:
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volume (Post Construction). | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track the features installed, size and treatment expectations as they are installed. | Ongoing as development occurs. | This strategy is tied into the Phase II program and dependent on funding availability to design and construct capital improvements, as well as on private investment in new or redevelopment projects. Report out on features being installed and maintained in capital projects that incorporate these. | All large capital road improvement projects in the City now implement LID stormwater improvements to be consistent with the Stormwater Management Manual. Several projects are currently in the design phase for future years with similar LID systems. The RC created an electronic survey form that can be used to inventory and map features (https://arcg.is/1Xe10i0). All tracking and other information collected is included in the City's stormwater program and included in the annual reports. No tracking was completed by the RC in 2023-2024. | Year 1: July 2020-June 2021:
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education through design workshops, volunteer opportunities, and/or other methods. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Part of phase II program. Annual update on program development and relevant statistics in Phase II report. | General information, workshops, volunteer opportunities, and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). Events, blogs, posts, and shared posts are used to advertise workshops and activities. In addition, Stream Smart features a pledge page to reduce impervious surfaces which tracks any user entered data which could include rain gardens. In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/), and information on the City's TMDL page on RVCOGs website (https://rvcog.org/grants-pass-tmdl/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Address water quality impacts of stormwater | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff Time, RVCOG, Partners, Regional MS4s, DMAs | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RC during the implementation year. The OWEB small grant program features a category for Urban Impact Reduction which could be used to fund BMPs. The RC will work with the City to evaluate potential funding for BMP implementation. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Pollution Prevention/Good Housekeeping - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage, sediment controls, street sweeping to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken in NPDES Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. More information can be found in the MS4 Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). | Review and refine illicit discharge and hot spot water sampling program as needed | Staff Time. RVCOG | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, | The RC serves a point of contact for regional water quality concerns. Calls that are received for Grants Pass and other jurisdictions are documented and referred to the appropriate entity, agency, or response including OERS, In addition, hot spot contact information including lists are available online through the Stream Smart program and are updated annually. The hot spot monitoring form is also used to record and document occurrences reported (https://arcg.is/1byiCy). More information can be found in the MS4 Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Annual update on actions taken in NPDES Phase II report. | As part of the IDDE program, the RC is available as directed by the City to conduct visual inspections of storm drains and areas of concern and document what is found. In addition, the RC can collect samples to see what the impact is on TMDL parameters. All activity is documented in the matrix. More information can be found in the MS4 Phase II report. No calls were received by the RM or City this year | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Annual update on actions taken in NPDES Phase II report. | Any activity will be included in the Phase II report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time. RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RC during the implementation year are reported to the City and/or DEQ. No concerns were reported this year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. | Staff time. RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The City and the RC continues to work with partners on programs to help protect and improve water quality conditions. With the expansion of the Stream Smart Program activities including the Adopt-A-River Program, Creek and River Clean-ups, and new partners (CWMA), we are looking to connect activities (e.g., restoration and clean-ups) to work on the Rogue River as a continuous corridor rather than a patchwork or mosaic. In addition, we are also looking for ways to get more information and data including mapping of activities and collecting additional water samples as time and funding permit. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Temp
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Implement current riparian buffer standards/riparian ordinance | Review site and land division proposals to ensure consistent buffers. Implement and enforce riparian ordinance | Staff Time | List of riparian buffer standards or riparian ordinance actions taken. | Ongoing | Annual reports will track buffer standards or riparian ordinance actions taken. | No activity/actions taken this implementation year by the RC. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Incentivize new land division proposals to reserve floodplains as a natural open space | Review site and land division proposals for opportunities | Staff time | Program development. Keep records of protected areas. | Ongoing | Annual reports and 5-year reviews will track progress including number of projects, acres preserved/restored, and establish recommendations for improvements as needed. | No activity/actions taken this implementation year by the RC. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for implementation of projects (active management of invasives, planting, etc.). RVCOG. Contractor(s), partners. | Line item established in budget with annual funding. | first year with line item and funding; annually thereafter | Budget development and reporting will demonstrate progress. Number of plantings or projects. | RC continues to work with the City to develop and implementing riparian restoration programs and remove invasive species. Support for riparian species restoration and invasive species removal projects are included in the contract with RVCOG. New sites for restoration are identified, surveyed, and mapped (Riparian Projects tab) during several field visits in the City. In addition, we worked with the County Weed Management Agency and the City to identify and implement projects for invasive species removal at Reinhart Park, in the Stream Smart Adopt-A-River Section, and as part of the Rogue River Clean-up. English Ivy, blackberry, starthistle, and other species were removed (4 acres). New this implementation year was beginning a project in Reinhart Volunteer Park (RVP) on restoration and a trail system that includes managing invasive species, working with volunteers to build the trail, planting pollinators, and restoring the riparian area along the Rogue River. 50 pollinator plants were planted as part of the pollinator garden in the RVP in addition to trail building and invasive species work by the City, local scouts, and volunteer groups (Dutch Brothers). Restoration maps for the City can be found on the restoration map on the City's TMDL page on the RVCOG website ( https://rvcog.maps.arcgis.com/apps/instant/nearby/index.html?appid=7b64357d6e364e9eb5fc7c5829b3f0a9&locale=en). While not located within the City, the Stream Smart program (supported by and funded by the City) included some restoration maintenance and watering as part of the Move For Your Water Event. The "Move" event was in partnership with the Rogue Drinking Water Partnership (RDWP) of which the City is a member. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. | Staff time, RVCOG, partners. | Completion and record of annual efforts | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | New sites are identified and catalogued using Survey 1-2-3. The sites are also prioritized using the riparian matrix developed in previous years. In addition, the City and RC continue to participate in regional programs with partners that focus on wider scale restoration activities including the Bear Creek Restoration Initiative (BCRI), and the Rogue Basin Restoration Working Group. In 2023-2024, the status of the RVP wetland project went from in development to active. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City participates in events: Events include at least one featured tree planting project, tree giveaways to residents, or restoration project activity (monitoring, maintenance, watering, invasive species management). | Staff time, RVCOG, partners. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | Events held each year with local participants and activities that educate and implement tree planting. | Most of the restoration (management of invasive species and planting or reestablishing natives) events completed in 2023-2024 were conducted under the Stream Smart program. Overall, nine events were held in the implementation year. Specifically, the City and RC worked with local scouts and volunteer groups (Dutch Brothers) in Reinhart Volunteer Park to plant pollinator species (35), build trails, and clear invasives. In addition, the RC coordinates the Jackson and Josephine County Cooperative Weed Management Areas (CWMAs). Members of the CWMA assist with invasive species removal at the Rogue Clean-up, participate in the Adopt-A-River Program, and other volunteer activities. The Stream Smart program included some restoration maintenance and watering as part of the Move For Your Water Event which was a program partnered with the Rogue Drinking Water Partnership (RDWP) of which the City is a member. Overall, an estimated 4 acres of invasives were treated in Grants Pass and Josephine County. Information on the events including number of volunteers, species planted, and other information can be found on the Volunteer tab located in the supplemental spreadsheet. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publically owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time, RVCOG, partners. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify Implemented projects on an annual basis | The City began work on the RVP wetland project. Funding was leveraged for signs , pollinator plants, labor, and other activities. Details are in the funding tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Reduce warm stormwater runoff volumes (Post Construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from stormwater utility fund, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects (mostly vegetative buffer strips and such associated with new road projects) that incorporated LID or other methods into development and redevelopment plans. | Any activity will be included in the MS4 report. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The focus of adaptive management related to restoration has been in building resiliency into restoration strategies to address fires, droughts, and other needs. The RC is working as part of the Bear Creek Restoration Initiative (BCRI) which developed a Natural Resources Plan containing general post fire restoration strategies for the entire Bear Creek Corridor focused on balancing multiple needs including wildlife and aquatic habitat benefits, water quality including providing shade. controlling invasive species, encouraging growth and re-growth, restoring pollinator habitat and floodplain function, building in fire and climate resiliency, access for fire fighting, considering public safety, recreation, the unhoused population, and other factors. It is anticipated that concepts and lessons learned from implementing this plan will be adapted for use in the general Rogue basin. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Ed and Outreach
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Report Notes | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter and/or other publications. | Staff. RVCOG. Partners. | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Articles, social media posts, and interviews are completed throughout the year on various topics related to the TMDL, Stream Smart, and Phase II programs. Posts, blogs, and articles are distributed through local media, the Stream Smart Program including its social media platforms, on the City's Websites, through partners, and the TMDL pages on RVCOG's website. Articles and interviews have featured the Creek and River Clean-ups including the Baker Park and Rogue Clean-ups, Restoration, Salmon Watch, Volunteer Opportunities, and other activities. Examples are included in the Articles and Blogs tab, and the Stream Smart Posting Examples. Additional information can be found on https://www.stream-smart.com/recent-posts/. Copies of the materials referenced in this report can also be found on the Bear Creek TMDL Page (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics | Staff time, RVCOG | City’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | The Stream Smart website is updated monthly (or more frequently as needed) with new content, links and/or events. In 2023-2024, the website was revised to be consistent with the outreach conducted in conjunction with the Ashland Change For Good Program. The GP TMDL website hosted by RVCOG website is updated quarterly and as needed and features copies of the TMDL reports, updates on activities, resources, reports, and links to other programs. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Example: Rain Garden, downspout disconnects, demonstration workshops, Salmon Watch Program, don’t feed wildlife etc. | Continue to support the Regional Programs by working with RVCOG. Additional Grants Pass specific programs will be conducted by City Staff, RVCOG, and/or volunteers. | Workshop/Program participation and measurable results (i.e. number of rain gardens installed, downspouts disconnected, number of students participating in Salmon Watch, etc.) | Annually | Annual Action Plan and Subsequent Report | Events have rebounded in terms of attendance post COVID and regional wildfires. Most of the programs covered in this table were conducted under the Stream Smart Program or Stream Smart was a key partner and coordinator. A full season of Salmon Watch was conducted in the Fall of 2023, with an additional hybrid program (Salmon Watch and Eggs-to-Fry Program release) held in December, and two days of a Spring Program in April of 2024 with Talent Middle School. Overall, through those programs, we completed 35 in person field days with 30 different schools. In addition, we worked with 20 different partners including DMAs and reached almost 2,000 students. The program served students and schools in both counties and Reinhart Volunteer Park was used as a Salmon Watch location. A detailed report can be found online (https://rvcog.org/wp-content/uploads/2024/08/General-Draft-Report-SW-Fall-2023-and-Spring-2024.pdf) The Rogue River Clean-up (May 2024) had 126 participants and picked up 7 cubic yards of trash and treated invasive species on 46 acres. In addition, there were 11 other volunteer activities volunteer events including the Baker Park Clean-up that were supported by the Stream Smart, the TMDL and Stormwater Programs had 173 attendees. Other events for the season included the Southern Oregon Regional Envirothon, staffing a booth and Ecoquest Activity as part of the Rogue Valley Earth Day, staffing booths at 2 other Earth Day Events including the Rogue Community College Redwood Campus, tabling for the Change For Good Program, work with the Jackson County Library District on the Salmon Watch Traveling Road Show, conducting regular activities as part of the Adopt-A-Greenway, Adopt-A-Street, and Adopt-A-River Program (Stream Smart Sections), working with Oregon State University's Student Watershed Assessment Team (SWAT), hosting events for the Move for Your Water, continuing to work with a Crater Renaissance Academy on activities on the Adopt-A-Greenway Section and serving on the Crater Renaissance Academy's Careers in Technical Education Board. Events and other activities reached more than 750 community members. We also presented programs including the Rogue River Clean-up and Salmon Watch at RVCOG Board Meetings, City Council Meetings, and a Chamber meeting in Grants Pass. Details on presentation and activities are included in the Activity Summary tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns | Staff time & support funding. | City’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report | The City of Grants Pass provides direct funding for the Stream Smart Program and participates as a member of the Advisory Committee. An example of Stream Smart activities can be found in the Stream Smart tab. In addition, the logo and social media platforms (Facebook and Instagram) are used to promote the City's programs including the Rogue River Clean-ups, programs with Dutch Brothers Volunteers, scouts, and community members. The RC works with Public Works and Parks during the year on activities related to the TMDL program, education, volunteering, and the Rogue Drinking Water Partnership. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Participate in a basin-wide riparian restoration program and provide outreach to target areas. | Staff time. RVCOG. Other DMAs. Partners. Volunteers | Focus is on identifying, prioritizing, and moving toward implementation of projects | Annually | Continued updating of projects identified, prioritized, mapped, and implementation status (pending, completed, ongoing). | New sites were identified and documented using Survey 1-2-3 and other methods. 10 sites were documented in 2020-2021. The locations of the sites are included in the map (Riparian Projects Map tab). Planting a restoration strategies that are used in restoration by the City follow recommendations found in the Bear Creek and Rogue Basin Planting Plan. Updates and changes to strategies follow recommendation completed by the Bear Creek Restoration Initiative and other groups. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. | Staff time. RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | The City has participated in meetings developing new technologies particularly in the form of electronic data collection forms for TMDL and stormwater using Survey 1-2-3 and online mapping. Funding provided by the City supported the creation of the forms, data collection, and mapping activities. The City also supports participation in programs looking at building resilience into TMDL implementation and developing strategies to address new variables including fires, drought, and other needs. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. | Staff time. RVCOG. Partners. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | TMDL implementation actions are tracked on an ongoing basis by RVCOG electronically through the use of surveys, maps, and/ or spreadsheets. In addition, data has been collected by the City as part of the Rogue Drinking Water Partnership to look at the impacts of the local fires (Almeda, Table Rock, and Obenchain) on the Rogue River and potential treatment and drinking water concerns. Data collected as part of this program was included in the data analysis for the Almeda Fire Monitoring Program and the City did contribute match for the project through data collection and participation in early stages of the project. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | RC staff provided updates to the City Council on the RVP wetland project. In addition, the RC attended a Chamber meet and greet to present on Stream Smart and the Clean-up. The RC updated the RVCOG Board periodically on TMDL related activities (e.g., Clean-ups, Stream Smart, Salmon Watch). A representative from the Grants Pass City Council is on the RVCOG | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | Staff attended quarterly meetings and provided updates during the roundtable updates. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Completed with the submittal of this document and accompanying forms. In addition, the City provides links to the annual reports through their TMDL page on RVCOG's website. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025