## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Update inventory of parks/public areas that have pet waste disposal dispensers. | Staff Time. RVCOG if needed. | Report on new stations installed and number of bags ordered. | Ongoing | Establish percentage of parks with stations. Add a percentage of stations added until 100% of parks have stations. | The City purchased 6,000 dog bags for $1,380.00 for use in the stations around the City. All parks have stations and no new ones are planned. If new stations are planned and/or installed, the City will provide updates in the annual reports. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Urban Runoff | Reduce runoff volumes (Post construction). | Continue to incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff through municipal codes and ordinances. | Staff Time, Work with RVCOG for tracking and funding support for projects (grants, partnerships) | Track the features installed, size and treatment expectations as they are installed by updating the LID map annually. | Ongoing as development occurs. | In Phase II report. Limited tracking and mapping completed by the Regional Manager (RVCOG) as requested. | The Regional Manager (RM) electronic survey form is available to inventory and map features (https://arcg.is/1zbb5e) that was created for regional use and will inventory DMAs as requested. Most annual work is completed under local Phase II programs and included in their annual MS4 reports. Any tracking and/or other information collected by the RM is included in the annual reports and added to these forms. In addition, online maps show up to date tracking (https://rvcog.maps.arcgis.com/apps/mapviewer/index.html?webmap=018eec42042b4216b7812956b974593f). No sites were inventoried by the RM in 2023-2024. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Encourage residential downspout disconnection, rain gardens. Provide educational opportunities including hands-on activities, resources, articles in newsletters/publications, and/or promote local workshops. | Staff time, Work with RVCOG, Partners. | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed. | Ongoing once the program is established. | Summarize overall activity including number of projects: number of downspouts disconnected, rain gardens constructed, and participants. | General information, workshops, volunteer opportunities, and other activities are available to the public through the Stream Smart Program (https://www.stream-smart.com/). In addition, information is also available on the Stormwater Page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/stormwater-101/) which includes a copy of the 2023-2024 Regional Stormwater Annual Report for Education and Public Involvement, and information on the TMDL page on RVCOGs website (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/). Most of the work completed in 2023-2024 under the TMDL program was on pollinator gardens which provide many of the benefits of the rain gardens, but are not specifically designed for that purpose. Pollinator gardens that were worked on or maintained include: Railroad Park, Medford Sports Park, Cascade Christian High School, and Peninger Road. The RM did lead a workshop at TRAILS outdoor school in Ashland that included a detailed discussion of stormwater management including the many features found on campus. Additional details on the program can be found in the Phase 2 Education and Outreach Report (https://rvcog.org/wp-content/uploads/2024/08/Annual-Report-2023-2024_8_28_24.pdf). In addition, resources a link to the Regional Stormwater Design Manual, the Rain Garden Guide (https://www.stream-smart.com/wp-content/uploads/2020/07/Rain-Garden-Guide.pdf) and the Planting for Stormwater Quality brochure (https://www.stream-smart.com/wp-content/uploads/2023/02/Planting-For-Stormwater-Quality.pdf) are available on the Stream Smart Website. | Year 1: July 2020-June 2020
Year 2: July 2021-June 2021
Year 3: July 2022-June 2022
Year 4: July 2023-June 2023
Year 5: July 2024-June 2024
|  | Implement WQ BMPs identified in the City’s Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. | No grant funds for implementation of Stormwater BMPS were pursued by the RM during the implementation year. Jackson SWCD does have a stormwater rebate program which could be used to fund smaller scale BMPs and was promoted as an option for the region. The RM will work with the DMAs as requested to evaluate potential funding for BMP implementation and apply for funding. Jacksonville is not a designated MS4, but does conduct stormwater related activities annually (staff, volunteers, or contracts with RVSS) including street sweeping and maintaining the storm drain system (street sweeping, ditch cleaning, creek cleaning, and storm drain cleaning). Details on the activities and cost ($17,490) can be found in the City Match Tab on the supplemental information spreadsheet (first tab). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Municipal Operations | Implement Stormwater Management Practices as time and funding permits. Examples activities include: Good Housekeeping, fleet maintenance, street sweeping, and site control (erosion) to prevent pollution to the maximum extent practicable. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. In Phase II report. | Information on the Eco-Biz program is on the Stream Smart website including the local contacts and a list of certified local fleets (https://www.stream-smart.com/our-work/programs-and-projects/ecobiz/) . In addition, several local municipalities and organizations are trained to complete inspections. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain). Part of Regional Monitoring Program. | Review and refine illicit discharge and hot spot water sampling program as needed. Participation in the regional TMDL programs addresses sampling of storm drains to evaluate their impact on TMDL pollutant levels, tracking and investigation of concerns as needed (or requested) especially related to TMDL concerns, and serving as a point of contact for water quality concerns. | Staff Time | Respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis, Annual report or regional activities generated by RVCOG. | As part of the TMDL program, the RM conducts visual inspections of storm drains as part of the stormwater monitoring program. Storm drain information is documented using survey forms and mapped. The visual data collected during the storm drain runs can be on the following map (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=573be1211ff644ed8d19c470f155fff1). The most recent survey was completed on July 17th, 2024 as part of the storm drain dry run. For the 2023-2024 monitoring season, the survey was completed in June of 2023. As part of the TMDL monitoring program, the RM visited 50 storm drains during the implementation period and collected 37 samples from storm drains. Some of the storm drains do not flow (especially during the low flow period), and some drains are unsafe to access at particular flows or due to overgrowth of weeds. Abnormally high readings of E/coli and other parameters are reported to the DMA and followed up on as needed as part of the hot spot monitoring program. In 2023-2024 reports were made to RVSS and Phoenix (bacteria levels at Blue Heron Park - TMDL site in February of 2024). The TMDL program also has a "hot spot" monitoring program to assist in identifying illicit discharges in partnership with the MS4 program or to serve as a major part of an IDDE program for jurisdictions that don't have their own programs (e.g., Jacksonville). Observations made are documented and reported to the appropriate DMA, agency, or OERS. A contact list is updated and distributed annually to the DMAs to help with communications between DMAs and also with the public. In addition, the RM investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). Concerns and actions are also documented in the activity summary tab and presented at quarterly TMDL meetings (by the RM, DEQ, and other as part of the TMDL Roundtable/Updates). Hot spot reports included a report of oil into a storm drain in Medford (December 2023), materials observed in two location in the White City Network to RVSS, MWC, and DEQ (December 2023), and Elk Creek to RVSS, Central Point, and Medford in April and May 2024. Concerns and actions are also documented in the activity summary tab. The Stream Smart website also contains information on reporting spills and contains the contact sheets (shown in the contact sheet tab). | Year 1: July 2020-June 2021
|  |  | Continued participation in regional program through RVCOG. |  |  |  |  | Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations. | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Part of phase I compliance. | Ongoing | Update on the number of investigations and any enforcement actions taken. Any activities tracked or responded to by RVCOG are including in the annual report of regional activities. | The RM investigates and documents areas of concern based on reports (calls), visual observations, and/or field results. Hot spots are documented using survey 1-2-3 and mapped (https://arcg.is/1vKDL0). 8 sites were logged this year. Details are provided above and in the referenced files and sheets. Example pictures are included in the hot spot tab. When hot spots occur in the City or are reported to the City, staff follows up and investigates. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. This could be summarized in the NPDES Phase II program report if applicable. | The City is not a designated MS4. The City works with regional partners (DEQ, RVCOG, RVSS) if there are concerns with erosion and water quality. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. | Any concerns identified by or reported to the RM during the implementation year are reported to the appropriate DMA, MS4, and/or DEQ. Concerns and actions are also documented in the activity summary tab. Data collected by the TMDL monitoring program is reviewed quarterly and sent to DMAs. Areas of abnormally high bacteria are discussed with DMAs and followed up on as needed. No referrals were made to the City in 2023-2024. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time. RVCOG. Partners | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | Monitoring data collected as part of the TMDL program and some additional sampling collected to evaluate contributions and impacts from the fire (including bacteria concerns) continue to keep tabs on the post fire restoration actions. 271 samples were collected by the monitoring program this year and include bacteria and other parameters of interest to the TMDL program. In addition, a comprehensive two year monitoring program funded by OWEB to study the long term impacts of the fire and look at where restoration efforts need to be focused and on what parameters was completed. Monitoring data collected as part of the normal TMDL and storm drain runs was used as part of the study. In addition, the TMDL program is providing in kind match to the monitoring program in data collection and analysis with the existing program and by collecting additional sampling in conjunction with ongoing monitoring runs. Data collected includes comprehensive metals and nutrients, 6 PPD Quinone, diesel and other hydrocarbons, and HABS (summer 2022). Over 300 samples were collected by the monitoring program this year and include bacteria and other parameters of interest to the TMDL program. In addition, there are several local efforts that are looking at ways to work on keeping the creeks cleaner and to continue with investigations of storm drains. For example, in May of 2024 there was a large effort undertaken by the City of Medford, the Community Livability Team, the RM, Plant Oregon, and others to clean-up trash from a large camp that is on the banks of Bear Creek. This effort was the first in working on a solution to removing the trash that enters to stream and also the impacts of camps which can included bacteria. In addition, there was an initial meeting of the Aquatic Trash Prevention Partnership in June which is looking at ways to increase awareness of trash and other materials entering Bear Creek including bacteria by focusing on pollution prevention. There is also continuing discussion on the next steps for investigation high bacteria levels in storm drains. There was analysis of data by DEQ with support from the RM that was presented at TMDL meetings. Several storm drains that result in consistently high bacteria levels are being discussed for follow up in future TMDL years. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Temperature
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Protect riparian areas by implementing current riparian protection standards | Implement current ordinance or riparian buffer standards. | Staff Time | List of actions taken. | Ongoing | Annual reports will track number and type of actions taken. | With the impacts of the Almeda fire, riparian restoration has been completed by members of the Bear Creek Restoration Initiative (BCRI) in partnership with the DMAs. All restoration projects meet the requirements of local ordinances and fall under the general conditions of the Bear Creek Natural Resources Plan (https://www.stream-smart.com/wp-content/uploads/2023/05/Bear-Creek-Final-NRP-Compiled_04.14.23.pdf), site prescriptions by individual BCRI members, and other local conditions. Projects including completed restoration projects are mapped as part of the BCRI maps. A link to the various story maps can be found here (https://storymaps.arcgis.com/collections/2edc8e9d597a4f39a22b9d59a531c1de?item=1). Known planting statistics by the RM and others are summarized below. An example of the story map is provided in the Restoration Project Map Example tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for restoration projects. This is a regional task in collaboration with RVCOG and/or other local groups. | Line item established in budget with annual funding. | first year program development and discussion, with line item and funding pending annually thereafter if program is established | Planting statistics, leveraged funding (including in-kind), and/or projects. This portion focuses on the implementation of restoration projects and builds on the DMA wide restoration program. This item will be a discussion item for Year 1 (2021-2022). | No specific line item has been established for restoration activities to date. TMDL funding provides general support and match for riparian restoration activities including identifying and prioritizing areas needing restoration, developing planting plans/recommendations, management of invasive species, organizing and participating in volunteer activities, planting native species (containers, cuttings, stakes), applying for grants, coordinating with other groups for restoration including coordination of the BCRI, and management of projects. Primary funding for on the ground implementation is leveraged through grants, volunteers, and partners (included in the funding leveraged tab. Much of the riparian restoration activity completed was related to the Almeda and Table Rock Fires and completed by members of the Bear Creek Restoration Initiative (BCRI) in partnership with the DMAs. Work completed by the RM (a member of BCRI) includes planting of native and pollinators at the Penninger Fire site, providing pollinators for projects at Cascade Christian, Railroad Park, and other projects. Approximately 500 native trees and pollinator species were planted along the Bear Creek Corridor. The City implemented a rebate program for blackberry abatement in the City focused on properties adjacent to natural waterways. Through this program, the City worked with 7 landowners, treated almost 3 acres of blackberries (estimated), and spent close to $8,000.00 on the program. A summary of the amounts and estimated acres by project can be found on the blackberry program tab. The City also has copies of before and after photos of the work completed that are available upon request. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. The regional program builds on the work completed in previous years and uses materials found in Bear Creek and Rogue Basin Planting Plans to prioritize and begin implementation. | Continue to participate in the regional program through RVCOG. | Completion and record of annual efforts (map updates, statistics, funding) | Annually | Provide updates on the status of sites in each DMA, new sites identified and prioritized, costs, schedule, and other logistics. Develop and annual goal for restoration (e.g., number of trees planted, miles restored, etc.). Outreach covered under the Education and Outreach Section. | The RM continues to work with the BCRI and local communities to develop and implement riparian restoration programs and remove invasive species. New sites for restoration were identified, surveyed, and mapped (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=82ba0e2dd6424e35b46cf24bf2dcb1aa). In addition, we continue to work with and coordinate the County Weed Management Agency to identify and implement projects for invasive species removal near the Expo Center, in the Table Rock (Central Point) area, and within the Almeda fire footprint. A map of the work being completed was developed and is being updated as new areas are completed or areas are re-treated (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=7c74710f96ed4742b5f2c8b917f1ff18). The maps also contain updates of project activities, status, and progress. A planting was completed on Rich Gulch Creek (26 shrubs and trees) by a private landowner in conjunction with work completed under the City's blackberry abatement program. The City covered the bulk of the blackberry removal which allowed for the planting to be completed. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Volunteer Planting Event(s) | City participates in events: Events may include at least one featured tree planting project or tree giveaways to residents. Events will be planned in the community, as part of an event (e.g. Fall Festival, Earth Day), incorporated into Salmon Watch (riparian section), and/or planned as a regional event. | Staff time. RVCOG. Partners. And/or volunteers. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | A minimum of one event held each year with local participants and activities that educate and implement tree planting. | Five volunteer events were held in the implementation year focused on restoration and planting. Three were focused on planting of restoration and fire sites and two were on site maintenance and restoration. Information on the events including number of volunteers, stakes planted, and other information can be found on the Volunteer Programs tab. In the City, Forest Park volunteers work on projects including education and outreach, trail building, working with school and volunteer groups, invasive species removal, planting/restoration, and other activities. In 2023-2024, volunteers provided 285 hours of in kind valued at $5,450.00. A summary of hours is included on the Forest Park Volunteer tab in the supplemental worksheet. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publicly owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time. Regional participation with RVCOG. Partnerships with local groups. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify (map) Implemented projects on an annual basis until 100% complete. If all public lands are completed, maintain plantings and add any new areas that become public. | New sites are identified and catalogued using Survey 1-2-3, Google Earth, and other methods. In addition, 15 sites were identified using Project Intake form following a workshop that was hosted by BCRI members including the RM. Sites were submitted by Medford, Central Point, Phoenix, ODFW, RM, TFT, and others. The map of restoration projects is updated on a regular basis and continues to be. In 2023-2024, story maps which include the project maps were created to help with tracking all restoration and invasive species work by multiple partners (https://storymaps.arcgis.com/collections/2edc8e9d597a4f39a22b9d59a531c1de?item=1). Four story maps were created: 1. Restoration, 2. Riparian Condition Zones (Planning), 3. Invasive Species Management, and 4. General Information (other data). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Stormwater Runoff | Reduce warm stormwater runoff volumes (post construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from streets, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects that incorporated LID or other methods into development and redevelopment plans | Jacksonville is not a designated MS4, but does work with Regional Partners on projects. For example, the City used porous pavers on an alleyway/parking for Doc Griffin park and placed one of the Stream Smart permeable pavers signs highlighting it's purpose. No projects were completed this implementation year. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals including identification of new invasive species of concern and control methods and new restoration techniques.. | Staff time. Regional programs through RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The focus of adaptive management related to restoration has been in developing strategies for restoring riparian areas using the Riparian Condition Zone model which developed general strategies for the entire Bear Creek Corridor focused on balancing multiple needs including wildlife and aquatic habitat benefits, water quality including providing shade. controlling invasive species, encouraging growth and re-growth, restoring pollinator habitat and floodplain function, building in fire and climate resiliency, access for fire fighting, considering public safety, recreation, the unhoused population, and other factors. A restoration workshop was held on June 13th (20 attendees) to provide an overview of the Natural Resources Plan and identification of projects that are included on the Restoration map. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025

## Education and Outreach
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under city jurisdiction (includes Dissolved Oxygen, pH, Nutrients) | Promote Cultural Awareness through Public Education and Involvement | Add TMDL or water quality related articles to city newsletter or other publication(s). Regional program will continue to promote and share TMDL topics on the Stream Smart website. The regional program will also provide general content for use on websites, in newsletters, etc. | Staff, RVCOG, Partners | Minimum of 2 articles published per year. Topic areas determined annually. | Annually | Annual report with copies of articles. | Articles, social media posts, and interviews are completed throughout the year on various topics related to the TMDL, Stream Smart, and Phase II programs. Posts, blogs, and articles are distributed through local media, the Stream Smart Program including its social media platforms, on DMA's Websites, through partners, and the TMDL pages on RVCOG's website. Articles and interviews have featured the Water Quality Press Release/Monitoring, Creek and River Clean-ups, Restoration, Salmon Watch, Volunteer Opportunities, and other activities. Examples are included in the Articles and Blogs tab, and the Stream Smart Posting Examples. Additional information can be found on https://www.stream-smart.com/recent-posts/. Copies of the materials referenced in this report can also be found on the Bear Creek TMDL Page (https://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/). The City features water quality and TMDL related information in it's newsletter and provides materials at City Hall. In June 2024, the City featured and article about Keeping Your Natural Watercourses Clean (copy in the supplemental materials matrix on the Copy of Newsletter tab). The information was also sent on a postcard to residents. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Maintain City’s web pages for Water Quality including stormwater and TMDL topics. Regional information will be updated on RVCOG's TMDL pages and the Stream Smart TMDL related pages as part of the regional TMDL participation. | Staff time, RVCOG | DMA’s web pages are regularly updated with relevant and informative information. In addition, the City's TMDL information will be updated on RVCOG's website and the Stream Smart Site as appropriate. | Ongoing | Annual Report summarizing changes & relevant links, if changed. | The Stream Smart website is updated monthly (or more frequently as needed) with new content, links, blogs, and events. Many of the education and volunteer activities that are part of the implementation programs form DMAs and/or MS4s are located on Stream Smart. In addition to updates, the RM and/or contractor(s) update the pages, checks for broken links, and other service related tasks needed to keep the site up and running. The RM also hosts TMDL related websites on RVCOG's website are updated quarterly or more frequently as needed. There are general TMDL pages for the Bear Creek TMDL The Rogue Basin TMDL, and the City of Jacksonville (https://rvcog.org/jacksonville-total-maximum-daily-load-tmdl-program/). There is also information and links to other related programs including BCRI, restoration maps, reporting, and other information. There are also cross links to and from DMA websites on the Stream Smart website as the DMAs (and MS4s) are major supporters of the program. The City has links to RVCOG, a citizen request tracker to report concerns to public works, and information on water conservation on their website that is updated annually. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Engage residents in experiential learning opportunities that promote awareness as well as tools for changing behavior. Examples of program that meet the TMDL goals that are done in partnership with other programs (NPDES Phase II) or just for the TMDL program include Salmon Watch, participation in local events (the Salmon Festival, Earth Day, Bear Creek Fall Festival), regional programs (Jackson SWCD Field Camp), programs with schools, partnerships with other groups, volunteer plantings, the August Institute, and other programs. | Continue to support the Regional Programs by working with RVCOG. | Workshop/Program participation and measurable results (number of projects completed, participants, etc.). | Annually | Annual Action Plan and Subsequent Report. | Events have rebounded in terms of attendance post COVID and wildfires. Most of the programs covered in this table were conducted under the Stream Smart Program or Stream Smart was a key partner and coordinator. A full season of Salmon Watch was conducted in the Fall of 2023, with an additional hybrid program (Salmon Watch and Eggs-to-Fry Program release) held in December, and two days of a Spring Program in April of 2024 with Talent Middle School. Overall, through those programs, we completed 35 in person field days with 30 different schools. In addition, we worked with 20 different partners including DMAs. The Fall Bear Creek Clean-up (September 2023) had 114 participants and picked up 4,895 lbs of trash and removed invasive species (estimated 0.5 acre). Statistics for the Spring clean-up were not available at the time of reporting with the exception of Pine Street in Central Point which had 52 volunteers, several clean-up location, planting (20 trees and shrubs), and maintenance of sites. In addition, there were 11 other volunteer activities volunteer events that were supported by the Stream Smart, the TMDL and Stormwater Programs had 173 attendees. Other events for the season included the Southern Oregon Regional Envirothon, staffing a booth and Ecoquest Activity as part of the Rogue Valley Earth Day, staffing booths at 2 other Earth Day Events, tabling for the Change For Good Program, work with the Jackson County Library District on the Salmon Watch Traveling Road Show, conducting regular activities as part of the Adopt-A-Greenway, Adopt-A-Street, and Adopt-A-River Program (Stream Smart Sections), working with Oregon State University's Student Watershed Assessment Team (SWAT), hosting events for the Move for Your Water, continuing to work with a Crater Renaissance Academy on activities on the Adopt-A-Greenway Section and serving on the Crater Renaissance Academy's Careers in Technical Education Board. Events and other activities reached more than 750 community members. The City conducts activities in Forest Park with schools, community groups, and volunteers. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Actively participate in the Stream Smart or other campaigns including promoting and using the program for relevant programs, sharing posts from online media, and submitting content as appropriate for social media use. | Staff time & support funding. | DMA’s webpage on Stream Smart website updated with relevant and informative information; participation in campaign planning & implementation. | Ongoing | Annual Action Plan and Subsequent Report. | The TMDL DMAs provide direct funding for the Stream Smart Program in conjunction with Phase II Programs and partners. As a result, there is overlap in program implementation and in subsequent reporting with many activities meeting the needs of both programs. The TMDL portion focuses on the dry weather portion of the TMDL and serves as the only participation for communities that don't have separate MS4 programs. Medford, Ashland, Jackson County, and Central Point participate as members of the Advisory Committee. In addition, Grants Pass and Josephine County also serve on the committee with the RM. Examples of Stream Smart activities conducted during the reporting year can be found in the Stream Smart tab. Funding provided by the DMAs and MS4s support the website (domain name registration, hosting, tracking, updates, contracted services for updates, content updates and addition (RM), event postings). In addition, the funding supports all related activities including marketing, postings, articles, meeting coordination, program promotion, development of materials (e.g. signs), and events and activities. In addition, DMAs participate in activities (e.g., instructing modules for Salmon Watch, participate in Clean-ups), have links to and from Stream Smart on their website, and use materials (logos, articles, posts) through the year as appropriate. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Provide outreach and technical support focused on riparian restoration activities. Includes tie in with the Stream Smart program, local assistance programs (Jackson SWCD), and the regional riparian program (Planting Plan including plant recommendations, site selection, invasive species recommendations). | Continued participation in the regional program. | Continued distribution of outreach materials, providing technical assistance to landowners, schools, and other groups. Providing continued support for assistance programs (e.g., SWCD riparian program). | Annually | Summary of activities and materials provided. | Planting sites are identified, mapped, and documented using Survey 1-2-3, Google Earth, and ArcGIS online. With the Almeda and Table Rock fires, the fire footprint area was identified as the primary area needing restoration. There are other areas that were not impacted by the fire that continue to be evaluated and prioritized for planting. Areas are identified by the RM, DMAs, BCRI members, partners, and others. Local prioritization (pre-fire) focused on the sites identified in the Bear Creek Restoration Initiative Restoration Plan. Information on these sites is on the BCRI information page (https://rvcog.org/bear-creek-restoration-initiative/). Post-fire, restoration is being directed and prioritized by the Bear Creek Natural Resources Plan, BCRI efforts, Envision Bear Creek, and funding that was received post fire for recovery and rehabilitation. In addition, as part of the prioritization of projects and updating the BCRI plan, a workshop was held to identify additional projects in June. Projects were submitted by or on behalf of Central Point, Phoenix, and Medford. In addition, the RM provides direct information and technical assistance at meetings, workshops, through phone calls, and other venues. Planting guidance and instruction is provided at all of the planting events. Topics included species selection, how to plant, goals of the planting (water quality protection, fish and wildlife habitat, managing fire risk and public safety, etc.). In addition, the RM serves as a point of contact for questions and refers partners, municipalities, schools, and the public to the appropriate entity, or resource (e.g., SWCD riparian rebate program when active), or the RM will provide technical assistance directly. Lists af activities are detailed in the activity summary tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | Explore new projects and program innovations to meet the goals of the TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals. | Staff time – potential coordination with RVCOG and local groups | New approaches will be in response to new technology, innovations or adaptive management. Can include trainings and workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops | The RM continues to work with both local and regional groups on educational and outreach programs. In 2023-2024, a portion of the restoration work and outreach was combined with the efforts of the Bear Creek Restoration Initiative. The RM worked as part of the BCRI Restoration and Stakeholder Engagement Working Groups to promote the work of BCRI and the Bear Creek Natural Resources Plan. The work led to the Bear Creek Summit in November 2023 which was attended by over 60 people and the RM was a speaker and the Bear Creek Restoration Workshop in June 2024 (20 attendees). At the June workshop, the RM worked on refining regional maps using an ESRI based platform and creating an electronic version of the intake form using Survey 1-2-3 to facilitate mapping efforts and also allow for field documentation of sites (https://arcg.is/00Ly8X1). We are also fostering new partnerships and opportunities to tie in other programs (e.g., drinking water and the Rogue Drinking Water Partnership). In 2024, we hosted an activity Make a Move For You Water which focused on combining the event with a restoration project in Stream Smart's Adopt-A-Greenway section. We also partnered with the Jackson County Library District for a summer program featuring a 1 hour version of the Salmon Watch Program "The Salmon Watch Traveling Road Show". The first class was held in June and attended by 12 people. Stream Smart has continued to focus more on social media activities than the website. In 2023-2024, we have 594 Facebook Followers and 250 Instagram Followers. Our Facebook reach was 15,000 and we had 1,4000 visits (an increase of 271% from last year). Instagram reach was 91 and we had 51 visits which was a 34% increase from previous year. The City initiated a blackberry abatement program to help control invasives along natural waterways. The program resulted in almost 3 acres of blackberries removed, 7 landowners participating, one paired restoration program, and spending almost $8,000.00 for local contractors and businesses to complete the work. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. RVCOG will continue to collect stream samples monthly at sites throughout the region. | Continued participation in the regional monitoring program. | Methods for tracking program effectiveness include sampling and analysis of water quality data (RVCOG, DEQ, other) load reductions, identification of trends, and tracking of TMDL actions. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results | The Regional Monitoring program continues to be a very successful part of the Regional TMDL Program. We collect over 350 samples annually from streams and storm drains (including the hot spot program). Data are analyzed overall and by season to look for patterns (see data analysis tab). In addition, we assign scores for the creeks annually based on exceedance data and creek a simple "score card" for the watershed for summer bacteria levels. We also look at the seasonal and annual patterns year to year to compare them to see if there are any long term patterns or trends. All water quality data is submitted to DEQ. TMDL implementation actions are also tracked on an ongoing basis by RVCOG electronically through the use of surveys, maps, and/ or spreadsheets. This tracking helps us to evaluate progress versus benchmarks. Specialized projects are also implemented to help look at specific concerns. In 2023-2024, monitoring data collected under an OWEB grant with in kind match provided by the TMDL monitoring program was analyzed and reporting was completed. Information on the fire monitoring project including reports can be found on (https://rvcog.org/almeda-fire-monitoring/) . | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
TMDL Reporting | Continued participation in TMDL Program | City will continue to update management on Stormwater/TMDL related actions | Staff Time, RVCOG as requested | City staff will keep city council updated on Stormwater/TMDL related actions | Ongoing | Report on number of updates given annually | No separate reports were given to management by the RM at DMA Council or Commission Meetings. Updates on projects including the Stream Smart Program, and clean-ups were given at RVCOG Board Meetings which include representatives from City Councils and County Commissioners. In 2024-2025, the City will work with RVCOG to provide an update to the Council on TMDL related activities. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will continue attend quarterly TMDL meetings. Regional TMDL support also provides support for the TMDL meetings. | Staff time | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by a representative from the city | DMA staff attended quarterly meetings and provided updates during the roundtable updates. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
|  | City will submit a TMDL annual implementation plan report yearly to DEQ. RVCOG will track and report on regional activities. | Staff time, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Reports Received | Completed with the submittal of this document and accompanying forms. Additional information including copies of the full supplemental materials (tabs) can be found online at https://rvcog.org/jacksonville-total-maximum-daily-load-tmdl-program/ | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025