## Bacteria
Bacteria (also addresses pH, Dissolved Oxygen, Nutrients)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Fecal sources from pets and wildlife. | Continue to provide pet waste bags for dog owners at local parks/public areas for owners to pick up after their pets. | Provide pet waste bags and trash cans for pet owners at local parks and public areas for owners to pick up after their pets. RM support as requested. | Staff Time | Track number of stations maintained and bags ordered. Any new stations will be added to existing inventories and maps. | Ongoing (annually) | Summary in annual report. Data submitted to regional manager (RM) will be summarized in the regional report. In addition, data provided in an ESRI or Google Earth Format will be added to the TMDL tracking maps on ArcGIS. As needed the RM can assist DMAs with surveying, tracking, mapping, and reporting. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Urban Runoff (ties to/supports Phase II programs and/or provides meeting basic goals for DMAs that are not MS4s) | Reduce runoff volume. Post Construction | Incorporate low impact development, green infrastructure approaches into capital improvements, development and redevelopment projects to reduce impervious areas and infiltrate runoff. RM support as requested. | Staff Time, Project Funding (utility fees & grants as applicable) | Track any features installed, detailing the size and treatment expectations as designed. | Ongoing as development occurs. | This strategy is dependent on funding availability for funding designs and construction of capital improvements, as well as private investment in new and redevelopment projects. Report and map features installed and maintained. As requested, RM can pursue funding for project implementation. Information/updates will be posted online. In addition, RM will map and track as needed including using forms designed in Survey 123 designed for tracking these features. Annual reports will summarize activity and provide links to relevant maps and spreadsheets. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Encourage residential downspout disconnection, rain gardens. Provide hands-on education activities through DMA channels, with partners, and RVCOG through the Stream Smart Program. | Staff time, Project Funding Work with RVCOG (SW Utility Fees, grants as applicable). | Track number of rain garden workshops held, number of downspouts disconnected, rain gardens constructed | Ongoing once the program is established. | Number of projects: number of downspouts disconnected, rain gardens constructed. Information on rain gardens, downspout disconnects, and other measures will be added to or updated on the Stream Smart website. In addition, Stream Smart can host workshops as requested and promote events through the Stream Smart website and social media platforms. The needs tie directly to the stormwater pledge program. Information will also be tie to the stormwater pages on the RVCOG website. RM will report on annual regional activities. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Implement WQ BMPs identified in the DMAs Stormwater Master Plan as funds are available. | Staff time, Stormwater fees, grant funds as applicable. | Program implemented over extended period | Ongoing | Report on BMPs implemented and any impediments. RM has survey forms available for tracking and can assist with tracking and mapping activities. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Lead by Example - Municipal Operations | Maintain Stormwater Management Practices including: Good Housekeeping, fleet maintenance, eco biz, proper material storage sediment controls, street sweeping to prevent pollution to the maximum extent practicable. RM support as requested. | Staff time | Ongoing inspections, employee trainings, and continued implementation of good housekeeping stormwater management practices. | Ongoing | Annual update on actions taken. RM can organize workshops through RVPSA or another venue as needed. In addition, RM can assist DMAs in summarizing existing procedures or recommending practices. RM participated in the Eco Biz training. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illegal dumping and illicit discharge | Continue illicit discharge monitoring (hot spot and storm drain) part of the RVCOG Monitoring program. | Review and refine illicit discharge and hot spot water sampling program as needed. RM will continue the storm drain and hot spot monitoring program that is part of the TMDL monitoring program. | RVCOG (RM) - This is included for all DMAs that participate in the Regional Monitoring Program. Staff Time to follow up on DMA specific concerns. | As part of the regional monitoring program, RVCOG staff respond to and investigate the potential sources of illicit discharge as discovered by the monitoring program. In addition, we also investigate concerns reported to us by the public, DMAs, partners, and agencies. We also conduct monitoring on storm drains throughout the watershed 3 times during the implementation year. Visual inspections occur as part of the site visit and the RM will document the inspections once per implementation year using Survey 1-2-3. | Ongoing | Report on illicit discharge and hot spot follow-up on an annual basis. Document concerns as appropriate using the hot spot monitoring forms. Annual report generated by RVCOG for regional activity. Hot Spot map updated as new reports are submitted. Data summary of all monitoring included in the annual report and links to the survey form for the storm drain inspections. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Continue to implement Illicit Discharge Detection Elimination Program and enforce illegal dumping regulations (MS4s). | Continue to investigate illicit discharges on an annual basis. | Staff time | Inspect city sewers to ensure no cross connections. Report any dumping or discharges to surface waters to DEQ. Can also be Phase II Compliance | Ongoing | Update on the number investigations and any enforcement actions taken. This could be summarized in the NPDES Phase II program report if applicable. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Erosion Prevention and Sediment Control | Continue to require erosion and sediment control at construction sites | Continue to implement NPDES Phase II program if applicable. | Staff Time | No visible sediment discharges from construction sites. Enforce construction erosion control permits if applicable | Ongoing | Summarize actions. This could be summarized in the NPDES Phase II program report if applicable. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Illicit Discharge - Septic Systems | Continue to Identify and eliminate failing on-site sewage disposal systems. | Notify DEQ of failing septic systems when found | Staff Time, RVCOG | Keep a written record of referrals. | Ongoing | Septic systems identified and eliminated. Any calls received regarding septic concerns will be logged, followed up ,and reported as part of the hot spot monitoring program as appropriate. In addition, monitoring results (bacteria) will also be reviewed periodically to identify areas of high bacteria levels. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Regional sources - Effectiveness Monitoring | Monitor and maintain awareness of bacteria levels in the Bear Creek watershed by monitoring creek sites and storm drains. | Monitor Creek temperatures. RM will continue conducting the water quality monitoring program. | RVCOG, Staff time for additional sampling outside of the monitoring program | Regional | Ongoing | Annual completion of monthly sampling and analysis for creek sites, and storm drains three times during the implementation year. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Bacteria TMDL. The RM will work with DMAs to explore new topics at TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the TMDL program. | Staff time, RVCOG | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. The RM (RVCOG) will work with DMAs to bring new topics to TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the bacteria TMDL. | Year 1: July 2025-June 2027
Year 2: July 2026-June 2028
Year 3: July 2027-June 2029
Year 4: July 2028-June 2030
Year 5: July 2029-June 2031

## Temperature
Temperature
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? |  | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation -Near Stream vegetation disturbance, removal, and invasives on Water's surface. | Develop or implement a restoration program to prioritize, restore, protect, and plant riparian corridors with native species and remove invasives. | Prioritize and seek opportunities to plant native trees and shrubs and remove invasives in public areas along waterbodies including streams, and rivers. RM will use the Bear Creek Natural Resources Plan, the Bear Creek and Rogue Basin Riparian Planting Plan, and other resources to identify and prioritize restoration projects. RM will work with DMAs, partners, volunteers, and through the Bear Creek Restoration initiative to develop and implement projects. RM will develop proposals, seek funding, provide letters of support, and/or manage projects. | DMA Staff, RVCOG, partners, contractors | Summary of any areas planted (or invasives removed) including number of plants, represented species, and distance (stream miles or area). In addition to the details above on regional projects, RM will update lists or maps of priority sites and provide links as appropriate. | Ongoing | Annual report will track number and types of actions taken. Add in projected linear feet or number of trees. Shrubs planted. Regional goal is 500 trees and 1 mile of stream restored. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Refine and implement maintenance programs for invasives as needed. Include staff training when provided by partners for noxious weed identification and control. RM will continue to work with the Cooperative Weed Management Area (CWMA) and TMDL partners on managing invasive species including working to provide educational opportunities and trainings, volunteer events, and on the ground management. | DMA Staff, RVCOG, partners, contractors | Trainings attended and maintenance performed (as applicable). Summary of annual activity with the CWMA including meetings, education programs, trainings offered, social media posts and shares (Stream Smart), acres treated, and other activities. | Ongoing | Annual report will track number and types of actions taken. Add in projected acres treated. Regional goals is 5 acres. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Submit request(s) for funding for restoration, planting and invasives removal at priority sites. RM will develop and submit requests for funding. | DMA Staff, RVCOG, partners, contractors | Summary of any funding sources identified and applications submitted. RM will reporting on any funding applied for and updates. | Ongoing | Annual report will document any funding applied , funding leveraged, and any status of ongoing applications. RM will summarize regional actions annually. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Apply and enforce Riparian ordinance/riparian buffer standards to protect existing native vegetation and canopy cover. For DMAs without formal riparian protection, modify this section to be consistent with what will be done under existing protection standards. | Apply riparian ordinance in review of land use applications and enforce violations of ordinance. | DMA Staff | Document enforcement actions and provide estimate of number of riparian violations. | Ongoing | Summarize actions in annual report. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Participate in a DMA-wide riparian restoration program. | Contract with RVCOG to implement program. RM actions are outlined in blue in the 'Develop or implement a restoration program….." | RVCOG | RVCOG report on riparian restoration program activities. RM actions are outlined in blue in the 'Develop or implement a restoration program….." | Ongoing as funding is available | Regional goals are 500 trees planted, 1 mile of stream restored, and 5 acres of invasives treated annually. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Educate property owners about the importance of shading and healthy riparian areas. | Pamphlets available in public areas (City Hall, County Offices), available on line, at events, through mailings, and/or direct outreach relating to riparian area health. RM will continue to educate property owners and the community through programs including Stream Smart (website content, posts, volunteer activities, riparian pledge), distribution of brochures, through Salmon Watch, outreach at community events, providing presentations, and/or other activities. Outreach events and volunteer activities will also provide trees and shrubs to projects and community members. | DMA Staff, RVCOG | Refill pamphlets when needed. Tracking and reporting on activities (# brochures distributed, # people reached, program details, examples of posts). | Ongoing | Annual report will track activities, number of people reached, brochures given out, and other metrics. Regional goal of a minimum of 250 residents reached through various programs. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Monitor and maintain awareness of temperature levels in the Bear Creek watershed by monitoring creek sites and storm drains. | Monitor Creek temperatures. RM will continue conducting the water quality monitoring program. | RVCOG, Staff time for additional sampling outside of the monitoring program | Trends in water quality indicate effectiveness of program. Report on water quality program and results in TMDL annual report. RM will send quarterly reports of all monitoring data to the DMA representatives which will include data summaries for the quarter. In the annual report, monitoring program activity will be summarized and analyzed. Results will be summarized in the report and any recommendations for changes included for the next implementation year. | Ongoing | Annual completion of monthly sampling and analysis for creek sites, and storm drains three times during the implementation year. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
| Explore new projects and program innovations to meet the goals of the temperature TMDL. The RM will work with DMAs to explore new topics at TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the TMDL program. | Staff, RVCOG | Summary of any new approaches will be in response to new technology, innovations or adaptive management. | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops in annual report. Summary of new topics at TMDL meetings, workshops, trainings, and other actions to meet the goals of the TMDL program. | Annually, as appropriate | Summary of actions in annual report. RM will summarize regional actions in annual report. | Year 1: July 2025-June 2027
Year 2: July 2026-June 2028
Year 3: July 2027-June 2029
Year 4: July 2028-June 2030
Year 5: July 2029-June 2031

## Education and Outreach
2025-2030 TMDL Implementation Plan
Education and Outreach
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Impacts to Temperature & Bacteria in waters under DMA jurisdiction (includes Dissolved Oxygen, pH, Nutrients). | Promote Cultural Awareness through Public Education and Involvement. | Add TMDL or water quality related articles to DMA newsletters, blogs, and/or other periodicals. RM will promote TMDL and water quality related materials through the Stream Smart Program, through RVCOGs TMDL Pages (regional and individual DMA), press releases, and other formats. | Staff, RVCOG (Stream Smart) | RM will complete a minimum of 4 articles, press releases, and/or blogs. DMAs to contribute additional articles. Topics will be determined through discussions at TMDL meetings, with DMA and the RM, or at other meetings. | Annually | Annual report summarizing activity. RM will complete a minimum of 4 articles, press releases, and/or blogs. Topic summaries, copies of articles, and/or links will be included in the annual reports. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Maintain DMA website for water quality including stormwater and TMDL topics. Add link to Stream Smart website to DMA website. RM will maintain the general TMDL and stormwater websites monthly, individual DMA sites as requested, and provide links to DMA websites from the Stream Smart website. The RM will also maintain and update the Stream Smart website in conjuction with the MS4 programs. | Staff, RVCOG (Stream Smart) | Completed updates to the appropriate webpages. Provide tracking statistics as relevant (e.g., Google Anlaytics for Stream Smart). | Ongoing | Annual Report summarizing changes & relevant links, if changed. RM will provide a summary of significant changes, relevant links to the websites, and any web tracking statistics (e.g. Analytics from the Stream Smart website). | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Engage residents in experiential learning opportunities that promote cultural awareness as well as tools for changing behavior. Examples may include: Rain Giarden Workshops, downspout disconnects, demonstration workshops, Salmon Watch Program. RM will continue to conduct educational programs for the TMDL and MS4 programs at local events (staffing booths), hosting workshops and trainings, teaching classes, coordinating with educational groups, hosting volunteer programs, organizing creek and river clean-ups, and conducting the Salmon Watch Program. Most of the activities are under the Stream Smart program including promoting the pledge and volunteer programs. | Staff, RVCOG (Stream Smart) | Documentation of all relevant statistics - Workshop/Program participation, number of rain gardens installed, downspouts disconnected, number of students participating in Salmon Watch, etc.). | Annually | Annual report summarizing outreach. RM will summarize activity in the annual report and provide links, photos, summaries, and other information on programs. RM will also provide updates at quarterly meetings and quarterly reports that will be posted online and emailed to DMAs. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Actively participate in the Stream Smart. RM will continue to maintain the Stream Smart website and social media platforms, coordinate with partners, market and promote events, recruit volunteers, sponsors, and partners, host advisory committee meetings and topic specific meetings (e.g., Salmon Watch), and continue to expand the program and program specific activities. | Staff, RVCOG (Stream Smart) | Link Stream Smart website to DMA website and provide link. Review link from Stream Smart to DMA website to ensure link goes to the correct department. Documentation of participation in Stream Smart activities. | Ongoing | Annual report summarizing outreach. RM will summarize activity in the annual report and provide links, photos, summaries, and other information on programs. RM will also provide updates at quarterly meetings and quarterly reports that will be posted online and emailed to DMAs. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Participate in a basin-wide riparian restoration program and provide outreach to target areas. RM will work through the Stream Smart program, with regional groups (e.g., Bear Creek Restoration Initiative), partners, and others to provide restoration outreach to target areas. | Staff, RVCOG (Stream Smart) | Focus is on identifying, prioritizing, and moving toward implementation of projects. Summarize number of projects and development stage in annual report. | Annually | TMDL annual report summarizing outreach and participation in the program. RM will summarize regional activities in annual report. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | Explore new projects and program innovations to meet the goals of the TMDL. The RM will work with DMAs to explore new topics at TMDL meetings, offer workshops, trainings, and other actions to meet the goals of the TMDL program. | Staff, RVCOG | Summary of any new approaches will be in response to new technology, innovations or adaptive management. | Annually, as appropriate | New approaches will be identified with success indicators determined. Can include attendance at trainings and workshops in annual report. Summary of new topics at TMDL meetings, workshops, trainings, and other actions to meet the goals of the TMDL program. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
Effectiveness Monitoring | Programs to track effectiveness of TMDL implementation | Working with DEQ, RVCOG or others implement water quality sampling program to evaluate and track program effectiveness. RM will continue conducting the water quality monitoring program. | RVCOG, Staff time for additional sampling outside fo the montoring program | Participate in regional monitoring program. | Annually | Trends in water quality indicate effectiveness of program. Report on water quality program and results in TMDL annual report. RM will send quarterly reports of all monitoring data to the DMA representatives which will include data summaries for the quarter. In the annual report, monitoring program activity will be summarized and analyzed. Results will be summarized in the report and any recommendations for changes included for the next implementation year. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
TMDL Reporting | Continued participation in TMDL Program. | DMAs to update Councils/Commissions on Stormwater/TMDL related actions. RM will continue to provide periodic updates at RVCOG Board meetings on TMDL related topics and present to Councils/Commissions or other groups as requested. | DMA Staff, RVCOG | DMA staff will keep the Board of Commissioners updated on Stormwater/TMDL related actions. | Ongoing | Annual report. RM will summarize activity in annual report. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | DMA will continue attend quarterly TMDL meetings. RM will continue to assist with organizing and hosting TMDL Quarterly meetings and other meetings on TMDL related programs. | DMA Staff, RVCOG | DMAs will participate in quarterly TMDL meetings either in-person or via phone. | Ongoing | Quarterly Meetings will be attended by DMA representatives. RM will host (or help arrange locations), attend meetings, and help facilitate meetings. | Year 1: July 2025-June 2025
Year 2: July 2026-June 2026
Year 3: July 2027-June 2027
Year 4: July 2028-June 2028
Year 5: July 2029-June 2029
|  | Continue to Participate in the TMDL program. RM will continue to provide logistical support to the TMDL program including managing program elements (e.g., water quality monitoring), coordinating partners and partnerships, distributing information, coordinating meetings, and providing other support as needed). | DMA Staff, RVCOG | Attendance (in person or via videoconference) at quarterly meetings and other meetings as requested. Summary of RM activities. | Ongoing | Attendance summary in annual report. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030
|  | DMA will submit a TMDL annual implementation plan report yearly to DEQ. RM will prepare an annual report summarizing activities completed for the regional program. Reports will be posted on the RVCOG website for the appropriate TMDL program. In addition, the RM is available for meeting with individual DMAs. | DMA Staff, RVCOG | Annual Implementation reports are Due November 1st for the preceding July 1 – June 30 reporting year. | Ongoing | Annual Report. RM will provide a report detailing regional activities and supplemental information for submittal to DEQ. Reports will also be posted on the RVCOG website. | Year 1: July 2025-June 2026
Year 2: July 2026-June 2027
Year 3: July 2027-June 2028
Year 4: July 2028-June 2029
Year 5: July 2029-June 2030