## 2018-2019
Source or Program | Meets Requirements for: |  | Strategy | Specific Actions [Recommend DMAs remove actions highlighted in red, either due to redundancy or action was completed in the first 5 year cycle] [Recommend changing RVCOG to RVCOG if DMAs are hiring RVCOG to coordinate or complete the action] | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost [For all actions specify DMA staff. Example: Public Works, Parks, Planning…] | Reporting Year or Plan Year [For all actions add a target date to the annual benchmark. Example: March TMDL meeting] | Status /Reporting Summary
| Bacteria | Temperature
I. Solar Radiation - streamside vegetation unprotected or inadequately protected. | X | X | A. Identify and inventory areas for protection. | 1. RVCOG and DMAs will update the map as new areas are identified. | 1. Copies of updated map(s). | RVCOG and DMA Staff | Annually. Review December TMDL meeting. Revision by June (year-end) | The Regional Manager updates the restoration map of existing and known projects with input from cities, Jackson County, watershed partners, and other local groups. Maps are reviewed quarterly and updated annually. Existing shapefiles are updated with: 1.) sites that have planted sites or sites that have moved into the active category and 2.) potential planting sites. The map is included in a separate tabs in the long form report (available online at http://rvcog.org/what-we-do/natural-resources/clean-water-act-tmdl/bear-creek-tmdl/) as an overall map and zoomed in sections that provide more detail. In addition, the RM continues to coordinate activities including basin wide mapping with the riparian working group and staff of the Rogue Basin Partnership (RBP). In 2018-2019, restoration project locations and activities (planted and projected) were tied into the mapping completed for the Bear Creek Restoration Initiative. In 2019-2020, the RM is creating an ArcGIS Online map with a survey (Survey 1-2-3) in partnership with the Bear Creek Restoration Initiative (BCRI) to collect data on all existing and planned projects along the Bear Creek corridor by all participating partners. The online map is anticipated to be finished in the 2019-2020 implementation year. Funding provided through the TMDL program allows the RM to work to integrate the work of the two programs.
|  | X | B. Prioritize areas for planting. | 1. DMAs and the RVCOG will use a GIS based process to prioritize projects throughout the watershed and incorporate new sites into the GIS based prioritization process. | 1. RVCOG will provide a list of prioritized sites by DMA. DMAs will provide input to assist in identifying and prioritizing sites. List of newly prioritized or reprioritized areas. | RVCOG and DMA Staff | Meetings, data collection, process overview - Year 1 Prioritized list - Year 2 Updated Annually as needed Years 3-5 | The project list is updated on an ongoing basis as new sites are identified and prioritized. In addition, with the input of the BCRI technical team, the RM identified and mapped priority areas for restoration needs. Examples of the maps produced are included as a tab in the full worksheet.
|  | X | C. Plant native trees and shrubs in public areas. | 1. RVCOG will identify restoration projects and other opportunities during each plan year, provide a planting and restoration project list, and work with DMAs and/or partners to coordinate and complete projects as time and funding permit. | 1. Summary of opportunities and activities identified and completed. The goal is to plant 500 trees in the watershed per year. | RVCOG, DMA Staff, Partners | Annually. Draft project list September TMDL meeting. March update and schedule of activities or activities completed. | Most of the activity this implementation year focused on planting the area near the Expo Center following the fire. Additional projects included finishing work on a section of Lazy Creek ay Lazy Creek Drive, and Larson Creek at Larson Creek Drive for the City of Medford. Over 700 trees and shrubs (including willow stakes) were planted in the watershed by DMAs working with the RM. Other groups conducting activity but not included in the tree count include Lomakasti Restoration, the Rogue River Watershed Council, ODFW, the Freshwater Trust (TFT) and Oregon Stewardship. See detail in I.C.4. The goal of 500 trees was achieved.
|  |  |  | 2. Identify resources and available funding to promote collaborative on-the-ground actions | 2. Identify and quantify staff resources, direct funding, equipment, in-kind labor, and other assistance available each year. | DMA Staff, RVCOG, Partners | Annually. Projected resources available September. Actual resources expended in June. | Funding available in 2018-2019 included $11,000 from Jackson SWCD, $7,500 from the Pacific Power Blue Sky Habitat fund, $2,000 from the Oregon Community Foundation, $9,740 from the City of Medford, and an estimated $5,000 from TMDL dues. In addition, the RM has an agreement with Jackson County for use of the Community Justice Crew for restoration and invasive species work. Several crew days (6) were used for planting and invasive species management projects. Other sources include in-kind from ODOT, Jackson SWCD, Oregon Stewardship, RVCOG, Crater High School, Local Scouts, and volunteers. Estimated volunteer hours for the program provided by partners and general volunteers is 1,231 hours. Estimated volunteer hours by activity is included in the Activity and Events Summary Sheet. Volunteer hours included participation in the clean-ups and volunteers for the Salmon Watch Program. See the funding leveraged tab for more information on grant applications and funded projects including riparian restoration.
|  | X |  | 3. RVCOG and DMAs will develop proposals and apply for funding and/or work with groups including the Freshwater Trust to protect and restore riparian areas. [In addition to parting with the FWT to restore private lands, cities need to continue to restore publicly owned lands and list a goal/measure of progress, such as number of trees planted, restoration projects completed, or area restored.] [DMAs should list proposed planting locations and timing for projects within their jurisdiction] | 3. List of projects, partnerships, or grant applications, including submittal dates, status (funded, not funded, pending), and general project location (DMAs and Creek(s)). | Grant funding, partners, general funds, staff. Specify project funding sources for each identified project. | Summary of activity annually | The Regional Manager and local DMAs continue to work with local partners to pursue opportunities for restoring the Bear Creek Watershed. During FY 2018-2019, the RM worked with the Freshwater Trust (Blue Sky Program), the Rogue Basin Partnership, the Rogue River Watershed Council, ODOT, the City of Medford, the City of Central Point, Jackson County Expo Center, Jackson Soil and Water Conservation District, Jackson County, Oregon Stewardship, and others on restoration and protection proposals in the Bear Creek Watershed. In addition, the RM facilitated the development of the Bear Creek Restoration Initiative (BCRI) which is a partnership of riparian practitioners, DMAs, nurseries, agencies and others who are working in restoration along Bear Creek. The BCRI is looking at ways to coordinate activities throughout Bear Creek and also look at the number of issues of managing Bear Creek and the Greenway. For private landowners, landowners were referred to the SWCD Landowner Assistance Program which provides technical assistance and funding for eligible projects which includes invasive species removal and planting/restoration of natives. Please see the detailed information in the funding leveraged tab for more information on project specifics.
|  | X |  | 4. Implement planting and restoration projects. Work with landowners to restore riparian areas. Specify projects if known. | 4. List of planned projects, projected completion dates, and actual completion dates. | General Funds. Volunteers. Grant funds (from C.2.2) | Summary of activity annually | Active restoration conducted by the RM (directly or in partnership with other organizations) included planting and invasive species management work includes the Penniger Fire area, Lazy Creek, and along the Bear Creek Greenway. Information on planting statistics can be found in tab I.C.4
|  | X | D. Riparian Ordinance - Protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under each DMAs jurisdiction. | 1. DMAs will enforce ordinance or new ordinance as needed [Cite ordinance number including reference to the listed creeks that are included in riparian protection ordinance. Track code variances] | 1. Annual reports will document enforcement and code variances. | DMA Staff – Code Enforcement Officer | Annually
II. Solar Radiation -Streamside vegetation removed or overrun by invasive species. |  | X | A. Manage invasive species in public areas. | 1. DMAs and RVCOG will summarize activities completed to manage invasive species in riparian areas. Activities will include management by DMA staff, regional activities, map(s) and/or activities completed by partners. [DMAs should list proposed management locations and timing for projects within their jurisdiction] | 1. Annual summary of Activities. The goal is to manage invasives in public areas including parks and rights of way. The goal is to treat 5 acres or 5% of public areas annually. Invasive weed management projects will be coordinated with restoration projects (and funding application) in I.C.3 | DMA Staff and RVCOG, Jackson County Weed Management area, and partners. | Annually [One project should be completed annually]. Proposed Project list by September. Actual projects in June to be included in the annual report. | Invasive species removal was conducted as part of all restoration projects (refer to tab I.C.4), for projects completed (approximately 11 acres). In addition, invasive weeds continue to be treated along the greenway and restoration projects from Jackson Street to McAndrews Boulevard and north. At the September 2018 and April 2019 events, 2 acres of blackberries was treated. Over 12 acres of invasives were removed meeting (and exceeding) the annual target of 5 acres.
III. Solar Radiation – Urban Forestry Program |  | X | A. Urban forestry program implementation to reduce thermal inputs from urban areas. | 1. DMAs will continue to implement programs. Plant street trees to reduce thermal loading on impervious surfaces. [DMAs should list proposed planting locations and timing for projects within their jurisdiction and address funding needs.] | 1. Program activity summary. Keep records of trees planted for new, redevelopment and street tree infill projects | DMA Staff [specify], tree costs funded by (?) | Annually | DMAs to add
IV. Fecal Sources – pet, wildlife, and livestock waste. Properly manage animal waste. | X |  | A. Provide bags for dog owners to pick up pet waste. | 1. Add any new or planned stations to inventory. | 1. Updated inventory and/or map. | DMA Staff | Annually | DMAs to add
| X |  |  | 2. Record number of bags purchased annually | 2. Document number of bags in matrix. | DMAs Staff or RVCOG | Annually | DMAs to add
| X |  | B. Manage animal waste - livestock. | 1. Partner with Jackson SWCD, ODA, and/or other groups to address livestock issues and concerns within the jurisdiction | 1. Document activity. | City of Ashland and RVCOG | Annually | Events related to managing livestock wastes are promoted through emails, event calendars (including on the Stream Smart website), at events, and through personal contacts. Concerns related to livestock waste and CAFO's are generally brought to the RM by the public, through partners, or observation of RVCOG staff. Concerns are followed up on by referring them to the appropriate agency which includes ODA for CAFO issues among and Jackson SWCD for their landowner assistance programs (non regulatory). Contacts are also logged in the Tracking and Reporting spreadsheet (included as the Activity and Event Summary Tab) for the TMDL program. No referrals were made during the implementation year. The updated "hot spot" contact lists contain contact information for animal waste concerns.
V. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | X |  | A. Illegal dumping/illicit discharge detection and elimination (IDDE) programs. | 1. DMAs and RVCOG will continue to work to implement and strengthen their IDDE programs through their the Phase II Stormwater programs and enforce illegal dumping regulations under the NPDES Phase II program and/or codes and ordinances. | 1. Phase II Annual Report. Submit report to the MS4 Stormwater Coordinator and submit an electronic copy with the TMDL annual report. | DMA Staff and RVCOG | Annually | The Illicit Discharge Monitoring program (storm drains and hot spot monitoring) is administered under the TMDL program. Data collected under the program, concerns, calls received, and other program elements are shared with local MS4s. All Bear Creek MS4s are also TMDL DMAs. In addition, the reporting deadline and reporting period for both programs are the same which facilitates program coordination when reports are submitted to MS4 coordinators. DMAs to add Phase II report.
| X |  |  | 2. Continue illicit discharge monitoring (hot spot and storm drain) as part of the monitoring program administered by RVCOG. Review and refine hot spot monitoring program as needed including updating the contact list. | 2. List of any program refinements, list of hot spot monitoring completed for the year, and copy of hot spot contact list. | DMA Staff and RVCOG | Annually | The RM implemented the illicit discharge monitoring program which includes the storm drain and hot spot monitoring program. Under the storm drain monitoring program, storm drains are visited 3 times during the year for visual inspections and for water quality sampling and analysis. 18 sites are monitored with additional samples collected at a randomly selected location for QA/QC (10% of samples) for approximately 60 samples collected annually. Samples are analyzed by RVCOG staff for bacteria, temperature, phosphorus, BOD, turbidity, conductivity, and pH. Reports are uploaded to the web after being sent to the TMDL committee for review. For the hot spot monitoring, the RM follows up on concerns observed in the field, as requested by DMAs and partners, or calls received from the public. Any public contacts made (calls received) are logged in the Activity and Event Summary spreadsheet including and follow up activities in the notes. The RM keeps a detailed log book of concerns that are followed up in detail in addition to the spreadsheet. In April and May 2019, RVCOG completed a study of two storm drains for the City of Medford evaluating potential sources of high bacteria levels recorded at outfalls over the past few years. Storm drain sampling data, hot spot contact sheets, stream postings, and other relevant information are uploaded to the Monitoring website on RVCOG's website http://rvcog.org/mn.asp?pg=NR_WQ_Monitoring. Information on how to report concerns including OERS contact information is also included on RVCOG's website and on the Stream Smart website. In 2018/2019, RVCOG completed a report summarizing the Storm Drain from 2013-2018 copies of the report can be found on the monitoring webpage following the link above. RM continues to implement the illicit discharge monitoring program and serves as a point of contact for water quality concerns. Other accomplishments included updating the hot spot contact list, uploading it to the website, and revising a monitoring form used for the visual inspections of the stormdrains. In 2019-2020, it is anticipated that the form will be converted to an electronic format and tied into ArcGIS online. The RM is also revisiting the public noticing procedure that is part of the TMDL program and will evaluate any tie-ins with this program.
VI. Urban Runoff – Reduce runoff, promote infiltration and low impact development practices, and control sediment. | X | X | A. Use of methods and practices that reduce urban runoff. | 1. DMAs and the RVCOG will continue to identify and implement low impact development practices through their Phase II Stormwater programs and/or municipal codes and ordinances. [ DMA must identify specific projects that will be implemented over the next 5 years.] | 1. Track the features installed, size and treatment expectations as they are installed or reference the pertinent sections in the NPDES Phase II annual Report. | DMA Staff and RVCOG [clarify if this action is completed by RVS under the Phase II Permit] | Annually | The RM participates as part of the Stormwater Advisory Team as part of their work with the NPDES Phase II Programs for the local MS4s and also works to coordinate between the two programs (TMDL and stormwater) to meet multiple objectives and where the program complement each other.
| X | X | B. Regional review and discussion of BMP databases and studies for treatment technologies (e.g., swales, wetlands, in-line systems) that will reduce bacteria levels in runoff. | 1. RVCOG will update the BMP database list and add new technologies as they are identified. DMAs will review and participate in a regional discussion regarding the use of the treatment technologies locally. | 1. Copies of updated list and recommended locations for installation of new treatment technologies. | RVCOG and DMA Staff | Annual Review of list Year-3 Hold a meeting or discuss technologies at quarterly TMDL and update list if needed following meeting. [Modify based on DMAs need] | RM reviewed the database. No updates were made this year. In 2019-2020, we anticipate discussing bacteria treatment BMPS to update and revise the list as needed.
| X | X | C. Inventory and map existing facilities installed in the Bear Creek watershed | 1. Review and update inventory and regional map of treatment facility locations. | 1. Inventory tracking form and map location of the features installed or reference to appropriate sections of the NPDES Phase II annual report. | RVCOG and DMA Staff | Annually | RVSS has completed online maps of facilities in Central Point and Talent available on https://rvss.maps.arcgis.com/apps/MapTour/index.html?appid=c4b907bf60dc40c99bd83e92cbbffe13. Ms4s have maps of these programs through their stormwater programs.
| X | X | D. Identify priority areas for installation of BMPs. | 1. Review and update list of priorities and locations or refer to appropriate sections of NPDES Phase II Plan. [ DMA must identify specific projects that will be implemented over the next 5 years.] | 1. Track the proposed features size and treatment expectations. | RVCOG and DMA Staff Project funding through (?) | Annually | Reported through MS4 programs.
| X | X |  | 2. Incorporate low impact development approaches into capital improvements, development and redevelopment projects in accordance with Rogue Valley Stormwater Quality Design manual to reduce impervious areas and infiltrate runoff. | 2. Track implemented features including relevant statistics (e.g., cost, size, treatment expectations.) | RVCOG and DMA Staff Project funding through (?) | Annually | Reported through MS4 programs.
VII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | X |  | A. Notify DEQ of failing systems when found. | 1. DMAs will notify DEQ of failing septic systems when found. | 1. Summary of any reported activity. Activity will be coordinated with NPDES Phase II MS4 programs. | DMA Staff and RVCOG | Annually | No septic system concerns were reported the RM this year.
| X |  | B. Cities will work with the NPDES Phase II programs, DEQ, and RVCOG to identify homes on septic systems within city limits. | 1. Develop an identification process and list of any homes on septic systems within city limits. | 1. Program summary and list of homes. | DMA Staff, DEQ, MS4s, RVCOG | Discuss procedures September 2014, March 2015 Complete method. List by June 2016. Updated Annually as needed. | The RM has completed preliminary review of monitoring data collected over the last few years and has summarized results in several reports. Hot spot identified in reports are being evaluated with data including land use, storm drainage networks, and sewer lines to see if there are potential ties with septic concerns. GIS analysis is being used to evaluate the land use, and proximity to waterways, drainage networks, and sewer lines to identify the taxlots. Taxlots will be identified in 2019-2020.
VIII. Outreach and Education | X | X | A. Implement regional outreach strategies targeting water quality parameters addressed in the TMDL. | 1. RVCOG and DMAs will coordinate with local groups (e.g., O.S.U. Extension, Bear Creek Watershed Education Partners, North Mountain Park, Coyote Trails, local schools) to implement outreach programs. RVCOG and DMAs will hold, participate in, and/or promote annual events benefitting TMDL related activities. | 1. Summary of events attended, activities/presentations conducted, and number of people attending and/or participating in activities. Attend a minimum of 3 outreach events per year for TMDL only or in partnership with other programs (e.g., NPDES Phase II, Riparian Restoration, etc.). | RVCOG and DMA Staff | Annually | Refer to the Activity and Event tab for specifics on events. Many events, but not all were done in conjunction with other programs, most notably the NPDES Phase II Stormwater programs (SW) and Stream Smart (STSM). Events and activities included: Rogue Valley Annual Earth Day Celebration at Scienceworks (STSM, SW and TMDL), two Bear Creek Clean-ups (STSM, SW and TMDL), RCC Earth Days (TMDL, STSM, SW) , the Land Steward Workshop (STSM, SW, and TMDL), the Bear Creek Salmon Festival (TMDL), the Bear Creek Fall Festival (STSM and TMDL), the Jackson County Field Camp (STSM, SW, and TMDL)and the Salmon Watch Program (SW and TMDL). Combined programs reached over 2,500 people including students and the general public (including adults). The top 10 Stream Smart Pages received over 12,000 visits (12,320) See events tab for photos of activities completed this year.
| X | X |  | 2. RVCOG and DMAs will provide and coordinate strategies with the Stream Smart Program and provide support to the Program as directed by the DMAs. | 2. Summary of activity and copies of or references to materials (brochures, web sections, etc.) in annual report. | RVCOG and DMA Staff | Annually | The RM coordinated and advertised events, trainings, workshops, clean ups, programs, and other activities with the Stream Smart program. Examples include the ongoing Adopt-A-River Program, the clean up events, the Bear Creek Fall Festival (Kids and Creeks), and Salmon Watch. In addition, the logo, event calendar, facebook website postings, and materials at events all helped to increase exposure for the Stream Smart program and attendance at the events/activities. The Stream Smart Logo has also replaced the logo collage on materials since it represents all of the TMDL DMAs and MS4s (and other). The RM coordinated the StreamSmart Advisory Committee which meets quarterly to identify needs of the program and make recommendations including how to keep it up and running, how to revamp and expand it, and identify needs and projects for the year. A large need identified for the program is to overhaul and update the website. Fundraising for this element is underway and updates are anticipated to be completed in 2019-2020. DMAs are supporting the program financially by funding the domain registration, website hosting, google email, and basic site maintenance.
| X | X |  | 3. RVCOG will adopt, customize, and/or develop regional materials to be used in the program and/or in coordination with the Stream Smart Program. | 3. Summary of activity. | RVCOG and DMA Staff | Annually | RM continued to develop, refine, and incorporate materials (including the logo and websites) for use in the program on an ongoing basis. Specific activities/items include developing a new pledge program focusing on pesticides in partnership with the Rogue River Watershed Council. Other materials included posters for the Salmon Watch Program, additional materials for the Bear Creek Fall Festival and Clean-ups, resources for the Salmon watch Program, signs for restoration projects, signs for riparian areas and the Salmon Life Cycle to go along the greenway, and the Resources Available to teachers for the August Institute.
| X | X |  | 4. RVCOG will assist DMAs in promoting regional success stories and other program activities through the local media, websites, newsletters, and/or other methods. | 4. Summary of activity and copies of any materials produced. | RVCOG and DMA Staff | Annually | RM regularly updates its website which features information on projects. In addition, throughout the year, the RM reports on activities at meetings, gives presentations, and provides information at events about regional successes. Specific successes and program activities include TMDL and Stormwater program implementation elements (leading to long term improvements in Bear Creek water quality), the Bear Creek Clean-ups, and the 2018-2019 Salmon Watch Program. A flyer on the success of the Salmon Watch Program is included on the Salmon Watch Stats tab. In addition, the success of and the upcoming Fall Events (Clean-up, Salmon Watch, and Bear Creek Fall Festival) were talked about on the Jefferson Exchange in August. The success of the Salmon Watch Program was highlighted on RVTV on their Adventures in Education Program in January.
|  | X | B. Provide citizens, landowners, and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. RVCOG and DMAs will work with local agencies, nurseries, landowners, and citizens to provide technical assistance and resources for planting. | 1. Summary of activities, contacts meeting, meetings, and presentations. | RVCOG and DMA Staff | Annually | RM participated in a number of events and activities throughout the year where resources were provided for citizens, landowners, and other groups. Examples include continuing to make referrals to the Jackson SWCD's Landowner Assistance Program, referring people to the Stream Smart website and Planting Pledge, recommending plants and resources were made at events (e.g., Land Steward Workshop, Earth Day, Bear Creek Clean Up, Salmon Festival), and distributing copies of the Stream and Wetland Enhancement Guide, Taking Care of Streams in Jackson County, and Garden Worthy Native Trees and Shrubs, and other riparian brochures were distributed were distributed. Information on the events and brochures distributed can be found in the Activity and Event Summary. In addition, we also worked directly with DMAs and partners on restoration projects that include plant recommendations, development of planting plans, and other materials. An example of a general planting plan can be found in the Planting Plan example tab in the full report.
|  | X |  | 2. DMAs and RVCOG will distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | RVCOG and DMA Staff | Annually | Copies of brochures are available on RVCOG's website. In addition, brochures handed out and locations are tracked in the Activity and Event Summary Tab. Brochures were distributed at libraries, to local businesses, at events including Salmon watch and where the RM (and others) staffed booths. In addition to visiting libraries, the RM worked with the Library District to distribute brochures and the Stream Smart Pledge Cards in English and Spanish to all of the libraries in Jackson County.
| X |  | C. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Outreach will continue to target areas of high animal usage including public areas near water ways and dog oriented businesses. | 1. Annual activity summary, documentation of deliverables including number and location of materials distributed, presentations, etc. | RVCOG and DMA Staff | Annually | RM helped organize the Bear Creek Fall Festival which is held at Bear Creek Park. The event targets park users including the Dog Park. In addition, the RM staffs a booth featuring information on Yard Care and the Stream Smart Program which includes pledges and poop dispensers for picking up after your pets. Information is also available on the Stream Smart website and facebook site including the pledges. Remaining poop dispensers and pledge cards were distributed at all events attended throughout the year, in geocaches, and at other locations.
| X | X | D. Staff Training [Modify to reflect staff training needs within your DMA and develop a training schedule. Include internal coordination and communication] [Could be stormwater BMPs, erosion prevention, pesticide use, roads maintenance, floodplain management etc...] | 1. DMA will train staff as needed on topics related to TMDL Implementation. RVCOG will compile, coordinate, and conduct staff training opportunities. | 1. List of how training was conducted and frequency. Activities may include classes, webinars, presentations, and seminars. | DMA Staff and RVCOG | Annually | Topics/presentations at quarterly TMDL meetings included - updates to the DEQ General Stormwater Permit, Cobi, the Water Quality Data Analysis Project, Fall Chinook Distribution from ODFW, and the Storm Drain monitoring program. A number of online webinars, local, regional, and statewide trainings were also promoted at TMDL meetings and through TMDL distribution lists by the RM, DMAs, and partners (e.g., RVSS).
IX. Regional Water Quality Coordination | X | X | A. Continue participation in the TMDL program. | 1. DMAs will continue participation in the TMDL program. RVCOG will continue to facilitate the meetings work with DEQ to develop agendas and arrange speakers. | 1. DMAs will send a representative to the quarterly TMDL meetings. RVCOG will provide a record of attendance and agenda topics for each meeting. Copies of completed sign-in sheets will be provided to DEQ. | DMA Staff and RVCOG | Annually | Funding provided by the DMAs supports the coordination of quarterly TMDL Meetings including developing agendas, facilitating meetings, arranging speakers, and providing program updates. Attendance records for all meetings were submitted to DEQ and provided on the TMDL meeting attendance tab.
X. Funding | X | X | A. Evaluate the costs of program implementation. | 1. RVCOG will work with DMAs to establish costs of regional program implementation including staff time, hiring of a RVCOG, existing grant funding, and other resources. [DMAs need to identify the cost of TMDL implementation for each action. Sources of funding from each DMA for each action needs to be noted (staff, grants, fees, or other sources), resulting in the development of a preliminary budget for implementing the next 5 years of implementation. Annual budgeting for specific projects will also need to occur.] | 1. Development of a preliminary budget for TMDL implementation which lists program costs and sources for all actions listed in the TMDL Implementation Plan Matrix (e.g., staff time, direct funding, grants, etc.). | RVCOG and DMA Staff with assistance from RVCOG | Annually | RM established the costs of several implementation items in developing the annual TMDL contracts. Additional implementation items including costs are provide in scopes for specific items and grant applications. A list of projected costs are listed in the funding leveraged tab.
| X | X | B. Seek additional funding for program implementation as needed. | 1. RVCOG will work with DMAs to apply for regional funding for implementation. [Develop a list of needs or projects eligible for grant funding and a schedule for applying for grant funding.] | 1. List of funding applied for and copies of grant applications as requested. | RVCOG and DMA Staff | Annually | The RM applied for and received funding through DEQ's 319 program (23,000.00), Jackson SWCD ($30,722), the Gray Family Foundation ($11,951.00), Rogue River Watershed Council ($7,500), the Oregon Community Foundation ($2,000) and the Rogue Basin Partnership ($1,000). The RM also received small grants and/or contributions for projects from SOLVE, Starbucks, REI, Fred Meyer, and Food for Less. Information on funding including applications can be found on the funding applications tab.
XI. Monitoring and Reporting | X | X | A. Use the matrix as a template to track the implementation plan Submit annual reports to DEQ. | 1. RVCOG and DMAs will compile information on the measures of progress and benchmarks into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. Completed annual reports submitted to DEQ by November 1st of each year, reporting on implementation actions for the July 1-June 30 plan year. | RVCOG and DMA Staff | Annually, September 30 of each year. | Tracking of activities is done by the RM regularly using calendars, spreadsheet, sign-in sheets, event reporting forms, field forms, and other methods. Additional detail is provided in reports, project summaries, online, and in invoices. Additional details for the report are included on separate tabs and/or in this reporting column. In addition, selected deliverables including completed matrixes are posted on the RVCOG and/or Stream Smart website.
| X | X | B. Use existing programs to track program effectiveness. [Specify how DMAs are tracking program effectiveness.] | 1. RVCOG will work with DEQ and the DMAs to implement methods for evaluating and tracking program effectiveness (e.g., surveys, check lists, meeting milestones and measures of progress). [Each DMA should specify how they are tracking program effectiveness.] | 1. Summary of methods evaluation and results. | RVCOG and DMA Staff | Year 3 [timeline based on selected method] | Currently, the RM tracks effectiveness through the monitoring program, attendance at events/workshops/trainings/meetings/etc, number of visits to the websites, number of brochures handed out, surveys, number of trees and shrubs planted, number of stream miles or acres protected, amount of invasive species managed (acres), mapping, and other methods. The top 10 Stream Smart Pages received over 12,000 visits (12,320). Please see the information on the Stream Smart Web Stats Tab for the visitor breakdown and most visited pages. Additional tracking information ia available on the Activity and Events Summary, I.C.4, and other tabs.
| X | X |  | 2. RVCOG will work with DEQ and the DMAs to use existing programs (TMDL monitoring program, DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. [Please be specific - RVCOG water quality data should be evaluated for trends and TMDL effectiveness] | 2. Summary of regional water quality. | RVCOG and DMA Staff | Year 3 [timeline based on selected method] | RVCOG collected and analyzed water quality samples in 2018-2019. Monitoring runs conducted include the monthly TMDL effectiveness run, bimonthly QA/QC splits with DEQ, hot spot monitoring, and the Illicit Discharge (storm drain) run. Sampling stations include streams and storm drains from the headwaters to the mouth of Bear Creek. Data is looked at on a monthly basis and quarterly or annual data is sent to the DMAs. A storm drain reports summarizing data from 2013-2018 was completed this year. In addition, the RM has been working with the Rogue River Watershed Council, the Freshwater Trust, and Oregon Department of Fish and Wildlife to find cold water refugia areas in Bear Creek by installing a series of in stream temperature loggers throughout Bear Creek (23 loggers). Details on monitoring runs including number of samples can be found in the Activity and Events Summary tab. Additional information including summary reports, data collected, and data analysis can be found on the monitoring homepage on RVCOGS website (http://rvcog.org/what-we-do/natural-resources/water-quality-monitoring/ ).In addition, data analysis to evaluate TMDL effectiveness is underway by EPA and should be finished in 2019-2020. Results of the analysis will be used to make changes to the TMDL implementation program and monitoring program (as needed).
| X | X | C. Adaptive Management Plan. | 1. RVCOG will assist DMAs to modify plan as needed. | 1. Revised TMDL Implementation Plans. | RVCOG and DMA Staff | Year 5 | Funding was applied through DEQ's 319 grant program to analyze the monitoring data collected over the last implementation to evaluate trends in the data and the effective of the TMDL implementation program. Work on the project is being completed in 2019-2020 and the results of the analysis will be used to make changes in the monitoring program and in the implementation program.