## 2019-2020
Source or Program | Meets Requirements for: |  | Strategy | Specific Actions [Recommend DMAs remove actions highlighted in red, either due to redundancy or action was completed in the first 5 year cycle] [Recommend changing RVCOG to RVCOG if DMAs are hiring RVCOG to coordinate or complete the action] | Measure of Progress/Benchmarks | Funding Analysis/ Estimated Cost [For all actions specify DMA staff. Example: Public Works, Parks, Planning…] | Reporting Year or Plan Year [For all actions add a target date to the annual benchmark. Example: March TMDL meeting] | Status /Reporting Summary
| Bacteria | Temperature
I. Solar Radiation - streamside vegetation unprotected or inadequately protected. | X | X | A. Identify and inventory areas for protection. | 1. RVCOG and DMAs will update the map as new areas are identified. | 1. Copies of updated map(s). | RVCOG and DMA Staff | Annually. Review December TMDL meeting. Revision by June (year-end) | The Regional Manager (RM) updated the restoration map of existing and known projects with input from cities, Jackson County, watershed partners, and other local groups. In 2019-2020, updates and mapping were moved to an electronic, updatable format using ArcGIS Online and Survey 1-2-3. A link to the map can be found here (https://arcg.is/14vSuP0) and a static image of the map is included on the map tab. In addition, planting shapefiles were submitted to Jackson County GIS and compiled as part of the TMDL reporting story map (TMDL Reporting Story Map).
|  | X | B. Prioritize areas for planting. | 1. DMAs and the RVCOG will use a GIS based process to prioritize projects throughout the watershed and incorporate new sites into the GIS based prioritization process. | 1. RVCOG will provide a list of prioritized sites by DMA. DMAs will provide input to assist in identifying and prioritizing sites. List of newly prioritized or reprioritized areas. | RVCOG and DMA Staff | Meetings, data collection, process overview - Year 1 Prioritized list - Year 2 Updated Annually as needed Years 3-5 | The project list is updated on an ongoing basis as new sites are identified and prioritized and also those needing additional work. 24 sites were prioritized as newly identified or needing additional work including maintenance or replanting (most in Bear Creek and one in Grants Pass). Sites were surveyed using Survey 1-2-3 and included the Bear Creek Restoration Initiative identified priority sites and other sites identified by the RM and DMAs. Sites were ranked using the methodology adapted from the Bear Creek Watershed and Rogue Basin Planting Plans that has been used in previous years. The Planting Prioritization tab has the newly listed and reprioritized sites. A map of the sites inventoried (red circles for the new sites, black diamonds for the BCRI sites, Green and yellow trees for previously identified sites is included on the Planting Map Tab.
|  | X | C. Plant native trees and shrubs in public areas. | 1. RVCOG will identify restoration projects and other opportunities during each plan year, provide a planting and restoration project list, and work with DMAs and/or partners to coordinate and complete projects as time and funding permit. | 1. Summary of opportunities and activities identified and completed. The goal is to plant 500 trees in the watershed per year. | RVCOG, DMA Staff, Partners | Annually. Draft project list September TMDL meeting. March update and schedule of activities or activities completed. | Activity this implementation year continued to focus on planting the burned area near the expo center following the fire coordinated by the RM. Planting was completed by Eagle Scouts, Middle Rogue Steelheaders, Lomakatsi, and others. Over 1,000 trees, shrubs, and pollinator plants were planted in the watershed (1,220).
|  |  |  | 2. Identify resources and available funding to promote collaborative on-the-ground actions | 2. Identify and quantify staff resources, direct funding, equipment, in-kind labor, and other assistance available each year. | DMA Staff, RVCOG, Partners | Annually. Projected resources available September. Actual resources expended in June. | Funding available in 2019-2020 included and an estimated $5,000 from TMDL dues. $15,000 from the City of Central Point, $5,000.00 from Jackson SWCD, and $2,500.00 from Pacific Power/Blue Sky. In-kind labor was provided by local scouts, the Middle Rogue Steelheaders, Jackson SWCD, and RVCOG. Work was also completed by Lomakatski and the Jackson County Community Justice Crew.
|  | X |  | 3. RVCOG and DMAs will develop proposals and apply for funding and/or work with groups including the Freshwater Trust to protect and restore riparian areas. [In addition to parting with the FWT to restore private lands, cities need to continue to restore publicly owned lands and list a goal/measure of progress, such as number of trees planted, restoration projects completed, or area restored.] [DMAs should list proposed planting locations and timing for projects within their jurisdiction] | 3. List of projects, partnerships, or grant applications, including submittal dates, status (funded, not funded, pending), and general project location (DMAs and Creek(s)). | Grant funding, partners, general funds, staff. Specify project funding sources for each identified project. | Summary of activity annually | The Regional Manager continues to work with local partners and pursues new opportunities with additional partners throughout the Rogue Basin. In 2019-2020, the RM worked with the RRWC on a proposal for Blue Sky/Pacific Power for the Expo Center Area and Bear Creek near Blue Heron Park. We received notice funding was awarded in June 2020. The RM also worked with Jackson SWCD and the City of Central Point to complete work near the Expo related to the Penniger Fire and with the City of Medford on a project along Larson Creek. In addition, we are working with and currently coordinating the Riparian Working Group of the Rogue Basin Partnership which looks at restoration across the basin including partnerships, funding opportunities, and general basin permits for approval of riparian projects rather than submitting projects for individual ODFW review. Additional detail on funding applications including riparian can be found in the Funding Tab.
|  | X |  | 4. Implement planting and restoration projects. Work with landowners to restore riparian areas. Specify projects if known. | 4. List of planned projects, projected completion dates, and actual completion dates. | General Funds. Volunteers. Grant funds (from C.2.2) | Summary of activity annually | RM created an activity tracking map to document completed and ongoing projects for TMDL implementation (https://arcg.is/0SjCGm0). A copy of the Map which includes these sites (Green and Yellow tree circles) can be found in the Planting Map tab.
|  | X | D. Riparian Ordinance - Protect existing native vegetation and canopy cover, and restore areas on all fish bearing streams under each DMAs jurisdiction. | 1. DMAs will enforce ordinance or new ordinance as needed [Cite ordinance number including reference to the listed creeks that are included in riparian protection ordinance. Track code variances] | 1. Annual reports will document enforcement and code variances. | DMA Staff – Code Enforcement Officer | Annually | Input needed.
II. Solar Radiation -Streamside vegetation removed or overrun by invasive species. |  | X | A. Manage invasive species in public areas. | 1. DMAs and RVCOG will summarize activities completed to manage invasive species in riparian areas. Activities will include management by DMA staff, regional activities, map(s) and/or activities completed by partners. [DMAs should list proposed management locations and timing for projects within their jurisdiction] | 1. Annual summary of Activities. The goal is to manage invasives in public areas including parks and rights of way. The goal is to treat 5 acres or 5% of public areas annually. Invasive weed management projects will be coordinated with restoration projects (and funding application) in I.C.3 | DMA Staff and RVCOG, Jackson County Weed Management area, and partners. | Annually [One project should be completed annually]. Proposed Project list by September. Actual projects in June to be included in the annual report. | Invasive species removal was conducted as part of all restoration projects (refer to tab I.C.4). Invasive species management work was conducted along Bear Creek near the Expo Center, in conjunction with the creek clean-ups, and as part of the restoration at Larson Creek.
III. Solar Radiation – Urban Forestry Program |  | X | A. Urban forestry program implementation to reduce thermal inputs from urban areas. | 1. DMAs will continue to implement programs. Plant street trees to reduce thermal loading on impervious surfaces. [DMAs should list proposed planting locations and timing for projects within their jurisdiction and address funding needs.] | 1. Program activity summary. Keep records of trees planted for new, redevelopment and street tree infill projects | DMA Staff [specify], tree costs funded by (?) | Annually | Provide input on activity (Medford, Ashland)
IV. Fecal Sources – pet, wildlife, and livestock waste. Properly manage animal waste. | X |  | A. Provide bags for dog owners to pick up pet waste. | 1. Add any new or planned stations to inventory. | 1. Updated inventory and/or map. | DMA Staff | Annually | Input needed.
| X |  |  | 2. Record number of bags purchased annually | 2. Document number of bags in matrix. | DMAs Staff or RVCOG | Annually | Input needed.
| X |  | B. Manage animal waste - livestock. | 1. Partner with Jackson SWCD, ODA, and/or other groups to address livestock issues and concerns within the jurisdiction | 1. Document activity. | City of Ashland and RVCOG | Annually | Concerns brought to the RM through the hot spot contact list, by the public, partners, and DMAs are followed up on by referring them to the appropriate agency which includes ODA for CAFO issues among. Any referrals or contacts made are also logged in the Tracking and Reporting spreadsheet (included as the Activity and Event Summary Tab) for the TMDL program. No referrals were made during the implementation year. Landowners in Jackson County who contact RVCOG with questions regarding livestock or help with on farm/ranch projects are generally referred to the SWCD for assistance through the landowner assistance program. The updated "hot spot" contact lists contain contact information for animal waste concerns.
V. Rural Residential and Urban Runoff –Develop programs to detect and eliminate contaminant discharges into waterways. | X |  | A. Illegal dumping/illicit discharge detection and elimination (IDDE) programs. | 1. DMAs and RVCOG will continue to work to implement and strengthen their IDDE programs through their the Phase II Stormwater programs and enforce illegal dumping regulations under the NPDES Phase II program and/or codes and ordinances. | 1. Phase II Annual Report. Submit report to the MS4 Stormwater Coordinator and submit an electronic copy with the TMDL annual report. | DMA Staff and RVCOG | Annually | The RM continued to implement the hot spot monitoring program for illicit discharge and the storm drain monitoring program. Under these programs, storm drains are visited 3 times during the year for visual inspection and sample collection for discharge water quality. 18 sites are monitored under the storm drain program with additional samples collected for QA/QC for approximately 60 samples collected per year. Samples are analyzed for bacteria, temperature, phosphorus, BOD, turbidity, conductivity, and pH. Reports are sent to the TMDL committee. In addition, the RM follows up on concerns observed in the field or as requested by DMAs or partners. Storm drain sampling data, hot spot contact sheets, stream postings, and other relevant information are uploaded to the Monitoring website on RVCOG's website http://rvcog.org/mn.asp?pg=NR_WQ_Monitoring. Information on reporting concerns is also included on RVCOG's website and on the Stream Smart website. In 2019 and 2020, a hot spot tracking form using Survey 1-2-3 was developed for the program and is being used to track ongoing concerns. In addition to the survey, an ArcGIS online map (https://arcg.is/1Gzr1z) showing the data was created. The map is updated as reports come in and are investigated. A storm drain visual inspection form is also being developed to assist in IDDE program and Illicit Discharge Monitoring Programs for the TMDL monitoring program.
| X |  |  | 2. Continue illicit discharge monitoring (hot spot and storm drain) as part of the monitoring program administered by RVCOG. Review and refine hot spot monitoring program as needed including updating the contact list. | 2. List of any program refinements, list of hot spot monitoring completed for the year, and copy of hot spot contact list. | DMA Staff and RVCOG | Annually | RM continues to serve as a point of contact for water quality concerns. The hot spot contact list was updated for the year (in July) and uploaded to the website. Concerns are referred to the appropriate contact, the Stream Smart website, and/or the Riverkeeper Swim Guide for information on bacteria levels in popular local swimming areas. In addition, information on the program including links to OERS and the contact lists are on the Stream-Smart and RVCOG's website.
VI. Urban Runoff – Reduce runoff, promote infiltration and low impact development practices, and control sediment. | X | X | A. Use of methods and practices that reduce urban runoff. | 1. DMAs and the RVCOG will continue to identify and implement low impact development practices through their Phase II Stormwater programs and/or municipal codes and ordinances. [ DMA must identify specific projects that will be implemented over the next 5 years.] | 1. Track the features installed, size and treatment expectations as they are installed or reference the pertinent sections in the NPDES Phase II annual Report. | DMA Staff and RVCOG [clarify if this action is completed by RVS under the Phase II Permit] | Annually | The RM participates as part of the Stormwater Advisory Team as part of their work with the NPDES Phase II Programs for the local MS4s. For the City of Jacksonville, the RM developed a survey to document and map features in the City and City owned properties.
| X | X | B. Regional review and discussion of BMP databases and studies for treatment technologies (e.g., swales, wetlands, in-line systems) that will reduce bacteria levels in runoff. | 1. RVCOG will update the BMP database list and add new technologies as they are identified. DMAs will review and participate in a regional discussion regarding the use of the treatment technologies locally. | 1. Copies of updated list and recommended locations for installation of new treatment technologies. | RVCOG and DMA Staff | Annual Review of list Year-3 Hold a meeting or discuss technologies at quarterly TMDL and update list if needed following meeting. [Modify based on DMAs need] | RM reviewed the database and is currently looking at where BMPs might be prescribed near specific stations to help reduce bacteria levels and move towards meeting TMDL goals in partnership with the 319 grant. BMPs to use in the current recommendations include continued riparian restoration, education and outreach programs, and regional facilities.
| X | X | C. Inventory and map existing facilities installed in the Bear Creek watershed | 1. Review and update inventory and regional map of treatment facility locations. | 1. Inventory tracking form and map location of the features installed or reference to appropriate sections of the NPDES Phase II annual report. | RVCOG and DMA Staff | Annually | RVSS has completed online maps of facilities in Central Point and Talent available on https://rvss.maps.arcgis.com/apps/MapTour/index.html?appid=c4b907bf60dc40c99bd83e92cbbffe13. Ms4s have maps of these programs through their stormwater programs. The RM completed an inventory and mapped facilities in Jacksonville (https://arcg.is/0LSCfq). The map also contains a few locations in Central Point.
| X | X | D. Identify priority areas for installation of BMPs. | 1. Review and update list of priorities and locations or refer to appropriate sections of NPDES Phase II Plan. [ DMA must identify specific projects that will be implemented over the next 5 years.] | 1. Track the proposed features size and treatment expectations. | RVCOG and DMA Staff Project funding through (?) | Annually | Reported through MS4 programs.
| X | X |  | 2. Incorporate low impact development approaches into capital improvements, development and redevelopment projects in accordance with Rogue Valley Stormwater Quality Design manual to reduce impervious areas and infiltrate runoff. | 2. Track implemented features including relevant statistics (e.g., cost, size, treatment expectations.) | RVCOG and DMA Staff Project funding through (?) | Annually | Reported through MS4 programs.
VII. Failing Septic Systems. Identify and eliminate failing on-site sewage disposal systems. | X |  | A. Notify DEQ of failing systems when found. | 1. DMAs will notify DEQ of failing septic systems when found. | 1. Summary of any reported activity. Activity will be coordinated with NPDES Phase II MS4 programs. | DMA Staff and RVCOG | Annually | No septic system concerns were reported the RM this year or noticed during field visits and sampling runs.
| X |  | B. Cities will work with the NPDES Phase II programs, DEQ, and RVCOG to identify homes on septic systems within city limits. | 1. Develop an identification process and list of any homes on septic systems within city limits. | 1. Program summary and list of homes. | DMA Staff, DEQ, MS4s, RVCOG | Discuss procedures September 2014, March 2015 Complete method. List by June 2016. Updated Annually as needed. | No activity in 2019-2020.
VIII. Outreach and Education | X | X | A. Implement regional outreach strategies targeting water quality parameters addressed in the TMDL. | 1. RVCOG and DMAs will coordinate with local groups (e.g., O.S.U. Extension, Bear Creek Watershed Education Partners, North Mountain Park, Coyote Trails, local schools) to implement outreach programs. RVCOG and DMAs will hold, participate in, and/or promote annual events benefitting TMDL related activities. | 1. Summary of events attended, activities/presentations conducted, and number of people attending and/or participating in activities. Attend a minimum of 3 outreach events per year for TMDL only or in partnership with other programs (e.g., NPDES Phase II, Riparian Restoration, etc.). | RVCOG and DMA Staff | Annually | Refer to the Meetings, Events, Activities tab for specifics on events. Many events, but not all were done in conjunction with other programs, most notably the NPDES Phase II Stormwater programs and Stream Smart. Fall events were completed as scheduled. Spring events were delayed, postponed, or conducted virtually to meet the socially distancing needs of COVID 19. Events and activities included: the Bear Creek Salmon Festival (TMDL), one Bear Creek Clean-up (SW and TMDL), the Bear Creek Fall Festival (TMDL and SW), and the Salmon Watch Program (Stormwater and TMDL). Combined programs reached over 2,000 people including students and the general public (including adults). There were also over 3,500 visitors to the Stream Smart website. See Activity Photos tab for photos of activities completed this year.
| X | X |  | 2. RVCOG and DMAs will provide and coordinate strategies with the Stream Smart Program and provide support to the Program as directed by the DMAs. | 2. Summary of activity and copies of or references to materials (brochures, web sections, etc.) in annual report. | RVCOG and DMA Staff | Annually | The Stream Smart program continues to expand primarily through the work and financial support of the TMDL DMAs and Stormwater MS4s. During this implementation year, 4 quarterly Stream Smart meetings and 2 website working group meetings were held in addition to sponsored activities, program implementation (Salmon Watch, Clean-ups), and events. Major accomplishments for the program included a major renovation of the website (http://test.stream-smart.com/) set to go live in the fall of 2020, drafting of bylaws for the program (anticipated to be adopted in September 2020), adding in additional partners (RDWP and the Pesticide Stewardship Partnership), an addition pledge (Pesticides), social media postings, creating new content, and linking a number of events and programs under the stream smart umbrella. We had almost 4,000 visitors to the top ten pages of the website. The top ten pages included pesticide and herbicides, A Day Without Water, The Bear Creek Fall Festival, about Bear Creek, Composting, and events. A Stream Smart survey was also conducted to evaluate regional perspectives on water quality. Selected results for Riparian Areas are summarized in the Stream Smart Survey Riparin Q tab.
| X | X |  | 3. RVCOG will adopt, customize, and/or develop regional materials to be used in the program and/or in coordination with the Stream Smart Program. | 3. Summary of activity. | RVCOG and DMA Staff | Annually | RM continued to develop, refine, adopt and customize for use in the program on an ongoing basis throughout the year. Almost all content created is related to the RMs involvement with educational and outreach programs including attending events and coordinating/participating in volunteer opportunities. Most of these programs are tied in to the Stream Smart program and feature but not limited to the logo (which represents all TMDL DMAs and Bear Creek MS4s), advertising on the events page, featured content on the website, and promotion on social media. In addition, material were adapted (and continue to be in the Summer and Fall of 2020) for COVID19 and features a lot of virtual programming. Specific examples include the Salmon Life Cycle posters adapted from some custom sign work completed by the RM, creation of two virtual programs for the Outside Every Day Programs in partnership with the MS4 program, creation of posters highlighting activities completed under the Clean-ups, updates of resource lists, posters, and activities for events, and other activities. Examples of items updated and/or created are included in the Regional Materials Tab.
| X | X |  | 4. RVCOG will assist DMAs in promoting regional success stories and other program activities through the local media, websites, newsletters, and/or other methods. | 4. Summary of activity and copies of any materials produced. | RVCOG and DMA Staff | Annually | RM regularly updates its website which features information on projects. In addition, throughout the year, the RM reports on activities at meetings, gives presentations, and provides information at events about regional successes. Additional successes are promoted on social media. In August 2019, the RM appeared on the Jefferson Exchange to promote the Stream Smart Program, the Bear Creek Fall Festival, Salmon Watch, and the Bear Creek Clean ups. Examples of materials promoted on social media include the clean-ups, virtual programs, Salmon Watch, Monitoring Programs, Water Quality Press Releases, Planting Projects, the Bear Creek Fall Festival, Stream Smart Pledges, and Geocaching.
|  | X | B. Provide citizens, landowners, and other groups with technical assistance and other resources to restore and protect riparian areas. | 1. RVCOG and DMAs will work with local agencies, nurseries, landowners, and citizens to provide technical assistance and resources for planting. | 1. Summary of activities, contacts meeting, meetings, and presentations. | RVCOG and DMA Staff | Annually | The RM participates in events and activities throughout the year where resources were provided for citizens, landowners, and other groups. Specifically, referrals are made to Jackson SWCD's Landowner Assistance Program, through the Stream Smart website and Planting Pledge. Recommendations for specific plants and resources were made at events (e.g., Bear Creek Clean Up, Salmon Festival), available online (lists), and through copies of the Stream and Wetland Enhancement Guide, Taking Care of Streams in Jackson County, and Garden Worthy Native Trees and Shrubs, and other riparian brochures distributed. Information on the events and brochures distributed can be found in the Meetings, Events, Activities tab.
|  | X |  | 2. DMAs and RVCOG will distribute technical information through mailers, websites, workshops, and/or provide documents at public offices. | 2. List of information and/or materials provided, and approximate numbers provided. | RVCOG and DMA Staff | Annually | Copies of brochures are available on RVCOG's website. In addition, brochures handed out and locations are tracked in the Activity and Event Summary Tab. Brochures were distributed at libraries, to local businesses, at events including Salmon watch and where the RM (and others) staffed booths.
| X |  | C. Distribute information to inform animal owners of the problems related to fecal waste. | 1. Outreach will continue to target areas of high animal usage including public areas near water ways and dog oriented businesses. | 1. Annual activity summary, documentation of deliverables including number and location of materials distributed, presentations, etc. | RVCOG and DMA Staff | Annually | RM helped organize the Kids and Creek event which is held at Bear Creek Park. The event targets park users including the Dog Park. In addition, the RM staffs a booth featuring information on Yard Care and the Stream Smart Program which includes pledges and poop dispensers for picking up after your pets. Information is also available on the Stream Smart website and Facebook site including the poop pledge which is used as one of the main links to reach out to pet owners.
| X | X | D. Staff Training [Modify to reflect staff training needs within your DMA and develop a training schedule. Include internal coordination and communication] [Could be stormwater BMPs, erosion prevention, pesticide use, roads maintenance, floodplain management etc...] | 1. DMA will train staff as needed on topics related to TMDL Implementation. RVCOG will compile, coordinate, and conduct staff training opportunities. | 1. List of how training was conducted and frequency. Activities may include classes, webinars, presentations, and seminars. | DMA Staff and RVCOG | Annually | Topics/presentations are quarterly TMDL meetings included the 319 Data Analysis project, ODFW discussing policy and approaches to riparian restoration after blackberry removal, the Clean River Coalition's Campaign for Stormwater Outreach, Education and Outreach reports, and Stream Smart Updates. In addition, a public information session for the draft 2018/2020 Integrated Report of Oregon's Impaired Water was held as part of/in conjunction with the October TMDL Meeitng
IX. Regional Water Quality Coordination | X | X | A. Continue participation in the TMDL program. | 1. DMAs will continue participation in the TMDL program. RVCOG will continue to facilitate the meetings work with DEQ to develop agendas and arrange speakers. | 1. DMAs will send a representative to the quarterly TMDL meetings. RVCOG will provide a record of attendance and agenda topics for each meeting. Copies of completed sign-in sheets will be provided to DEQ. | DMA Staff and RVCOG | Annually | Funding provided by the DMAs supports the coordination of quarterly TMDL Meetings including developing agendas, facilitating meetings, arranging speakers, and providing program updates. Attendance records for all meetings were submitted to DEQ and provided on the TMDL meeting attendance tab. With COVID19 impacting meetinhs later in the Year, TMDL work shifted to preparing for the new implementation plans including expectations, surveys, and drafts.
X. Funding | X | X | A. Evaluate the costs of program implementation. | 1. RVCOG will work with DMAs to establish costs of regional program implementation including staff time, hiring of a RVCOG, existing grant funding, and other resources. [DMAs need to identify the cost of TMDL implementation for each action. Sources of funding from each DMA for each action needs to be noted (staff, grants, fees, or other sources), resulting in the development of a preliminary budget for implementing the next 5 years of implementation. Annual budgeting for specific projects will also need to occur.] | 1. Development of a preliminary budget for TMDL implementation which lists program costs and sources for all actions listed in the TMDL Implementation Plan Matrix (e.g., staff time, direct funding, grants, etc.). | RVCOG and DMA Staff with assistance from RVCOG | Annually | RM established the costs of regional implementation items in developing the annual TMDL contracts and costs have remained the same for Year 5 implementation for the monitoring, education, and implementation items. Plans were revised this year and costs for Year 1 were calculated based on existing budgets. Costs for future years will be developed in each year, but are not anticipated to increase greatly assuming grants (or other sources) provide funding for large implementation projects (e.g., on the ground restoration of large areas). Additional implementation items including costs are provide in scopes prepared for individual DMAs by request and/or for grants or partner support. Specific TMDL related scopes/grants have included riparian restoration, invasive species management, additional water quality services, trainings, workshops, and educational activities. In addition, part of the Stream Smart Program (basic updates and keeping the website up and running) is included as part of the TMDL contracts in addition to the major website update (website funded in conjunction with Phase II).
| X | X | B. Seek additional funding for program implementation as needed. | 1. RVCOG will work with DMAs to apply for regional funding for implementation. [Develop a list of needs or projects eligible for grant funding and a schedule for applying for grant funding.] | 1. List of funding applied for and copies of grant applications as requested. | RVCOG and DMA Staff | Annually | The RM works with DMAs and partners to write grants and leverage funding for implementation and activities. Funding applied for includes restoration projects on Bear Creek Near the Expo from Central Point and the Blue Sky Pacific Habitat fund. Bear Creek at Blue Heron Park (in partnership with RRWC on the Blus Sky Proposal). Salmon Watch supporting funds for contractors, supplies, travel, and other logistics (permits, parking) from the Grey family foundation. The RM also received small grants and/or contributions for projects from SOLVE, Starbucks, REI, Fred Meyer, and Food for Less. Information on funding applications can be found on the funding applications tab. In terms of prioritization, the RM using tools including the Bear Creek and Rogue Basin Riparian Planting Plan and subsequent prioritizations(Planting Prioritization tab), the results of the Bear Creek Riparian Restoration Initiative Report, Monitoring Data, DMA and partner request, and other metrics. The RM also participates in regional working groups and meetings to help with prioritization of projects, in leveraging funding, in implementing projects, and in partnering on grant applications.
XI. Monitoring and Reporting | X | X | A. Use the matrix as a template to track the implementation plan Submit annual reports to DEQ. | 1. RVCOG and DMAs will compile information on the measures of progress and benchmarks into the matrix to track TMDL implementation activities. | 1. Tracking of activities using the matrix. Completed annual reports submitted to DEQ by November 1st of each year, reporting on implementation actions for the July 1-June 30 plan year. | RVCOG and DMA Staff | Annually, September 30 of each year. | Tracking of activities is done by the RM regularly using calendars, spreadsheets, online summaries, and reports at meetings. In addition, the RM completes the regional matrix and associated deliverables and posts on the TMDL pages on RVCOG's website. Details from our tracking are included on separate tabs including the Meetings, Events, Activities tab. In addition, selected deliverables including completed matrixes are posted on the RVCOG and/or Stream Smart website throughout the year and are featured in social media campaigns (e.g., Salmon Watch, Clean ups, Bear Creek Fall Festival).
| X | X | B. Use existing programs to track program effectiveness. [Specify how DMAs are tracking program effectiveness.] | 1. RVCOG will work with DEQ and the DMAs to implement methods for evaluating and tracking program effectiveness (e.g., surveys, check lists, meeting milestones and measures of progress). [Each DMA should specify how they are tracking program effectiveness.] | 1. Summary of methods evaluation and results. | RVCOG and DMA Staff | Year 3 [timeline based on selected method] | Currently, the RM tracks effectiveness through the monitoring program by looking at the data from the sampling and analysis throughout the watershed, by tracking attendance at events/workshops/trainings/meetings/etc., the number of visits to the websites, number of brochures handed out, surveys completed, number of trees and shrubs planted, number of stream miles or acres protected, amount of invasive species managed (acres), mapping, and other metrics. The Stream-Smart website had 3,859 visitors to the top ten pages. Please see the information on the Stream Smart Web Stats Tab for the visitor breakdown and most visited pages. In addition, the RM works with DMAs and partners on other methods to with tracking and effectiveness. In 2019-2020 (and continuing into 2020-2021), the RM has been working with DEQ, EPA, and others to evaluate the monitoring data collected for the last 5+ years. The project is looking for statistically significant treands that would answer questions about how effective the implementation efforts have been. Results of the study are being evaluated. In 2020-2021, work will be completed and evaluating next steps including hosting working group meeting(s) to look changes to the monitoring program and/or recommended management strategies. The RM has also been working with the Rogue River Watershed Council, the Freshwater Trust, and Oregon Department of Fish and Wildlife to find cold water refugia areas in Bear Creek by installing a series of in stream temperature loggers throughout Bear Creek (23 loggers). Data from the loggers will be used to identify potential refugia areas, evaluate the impacts of the drought, and also to evaluate effectiveness of restoration projects. This is the fourth year of the temperature monitoring project. DEq also sponsored a survey in preparation for the new implementation plans that looked at evaluating what has worked and what hasn't, and to help identify some needs. The RM assisted in promoting the survey and completing surveys or portions of surveys.
| X | X |  | 2. RVCOG will work with DEQ and the DMAs to use existing programs (TMDL monitoring program, DEQ Water Quality Index Stations, etc.) to evaluate program effectiveness. [Please be specific - RVCOG water quality data should be evaluated for trends and TMDL effectiveness] | 2. Summary of regional water quality. | RVCOG and DMA Staff | Year 3 [timeline based on selected method] | RVCOG collected and analyzed water quality samples in 2019-2020. annually, the RM collects samples from over 350 sites and processes over 2300 analysis in the field and lab. Monitoring runs conducted included the monthly TMDL effectiveness run, bimonthly QA/QC splits with DEQ, hot spot monitoring, and the Illicit Discharge (storm drain) run. Sampling stations include streams and storm drains from the headwaters to the mouth of Bear Creek. Data is evaluated on a monthly basis/. Quarterly data reports are to the DMAs. In addition, annual data is also submitted to DEQ. In 2019-2020 and 2020-2021, data is being evaluated by station in conjunction with the 319 grant to look at conditions throughout the watershed. Management strategies/bmps are being evaluated to recommend at selected sites to help improve program effectiveness. The RM is also working on watershed report card and has completed a draft for 2018 and 2019 with Bacteria and Phosphorus. The report card provides a visual tool to evaluate how the watershed is doing as a whole and to be able compare between years. The work is part of a larger effort looking at the Rogue Basin.
| X | X | C. Adaptive Management Plan. | 1. RVCOG will assist DMAs to modify plan as needed. | 1. Revised TMDL Implementation Plans. | RVCOG and DMA Staff | Year 5 | The RM worked with DMAs to update their plans for the next 5 year cycle using guidance provided by DEQ drafts were submitted in June with finals due in August. The format of the plans changed to follow the DEQ guidance, but the plan content remained largely the same. However, the new plans move from planning elements to more implementation activities.