## Temperature
Temperature (also addresses Dissolved Oxygen)
Source | Strategy | How | Fiscal Analysis | Measure | Timeline | Milestone | Activity Update | Annual Status Update
What source of this pollutant is being addressed? | What is being done or what will be done to reduce or control pollution from the source? | Specifically, how will this be done? | Who will implement? | How will successful implementation or completion of this strategy be measured? | When will the strategy be completed? | What intermediate goals will be achieved and when? How to know progress is being made? | What intermediate goals will be achieved and when? How to know progress is being made? | Briefly report on actions taken to meet this measure and achieve this milestone
Solar Radiation. Riparian health due to insufficient or unprotected riparian vegetation. | Protect riparian areas by implementing current riparian protection standards | Implement current ordinance or riparian buffer standards. | Staff Time | List of actions taken. | Ongoing | Annual reports will track number and type of actions taken. | With the impacts of the Almeda fire, riparian restoration has been completed by members of the Bear Creek Restoration Initiative (BCRI) in partnership with the DMAs. All restoration projects meet the requirements of local ordinances and fall under the general conditions of the Bear Creek Natural Resources Plan (https://www.stream-smart.com/wp-content/uploads/2023/05/Bear-Creek-Final-NRP-Compiled_04.14.23.pdf), site prescriptions by individual BCRI members, and other local conditions. Projects including completed restoration projects are mapped as part of the BCRI maps. A link to the various story maps can be found here (https://storymaps.arcgis.com/collections/2edc8e9d597a4f39a22b9d59a531c1de?item=1). Known planting statistics by the RM and others are summarized below. An example of the story map is provided in the Restoration Project Map Example tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Develop or participate in a Riparian Restoration Program to remove invasive species and plant or restore native species along stream corridors. | Partner with others including RVCOG to provide logistics and labor for invasive removal, planting & ongoing maintenance | Establish a line item in the Budget for restoration projects. This is a regional task in collaboration with RVCOG and/or other local groups. | Line item established in budget with annual funding. | first year program development and discussion, with line item and funding pending annually thereafter if program is established | Planting statistics, leveraged funding (including in-kind), and/or projects. This portion focuses on the implementation of restoration projects and builds on the DMA wide restoration program. This item will be a discussion item for Year 1 (2021-2022). | No specific line item has been established for restoration activities to date. TMDL funding provides general support and match for riparian restoration activities including identifying and prioritizing areas needing restoration, developing planting plans/recommendations, management of invasive species, organizing and participating in volunteer activities, planting native species (containers, cuttings, stakes), applying for grants, coordinating with other groups for restoration including coordination of the BCRI, and management of projects. Primary funding for on the ground implementation is leveraged through grants, volunteers, and partners (included in the funding leveraged tab. Much of the riparian restoration activity completed was related to the Almeda and Table Rock Fires and completed by members of the Bear Creek Restoration Initiative (BCRI) in partnership with the DMAs. Work completed by the RM (a member of BCRI) includes planting of native and pollinators at the Penninger Fire site, providing pollinators for projects at Cascade Christian, Railroad Park, and other projects. Approximately 500 native trees and pollinator species were planted along the Bear Creek Corridor. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Participate in a DMA-wide restoration program and provide outreach to target areas. | Identifying, prioritizing, and moving toward implementation of projects. The regional program builds on the work completed in previous years and uses materials found in Bear Creek and Rogue Basin Planting Plans to prioritize and begin implementation. | Continue to participate in the regional program through RVCOG. | Completion and record of annual efforts (map updates, statistics, funding) | Annually | Provide updates on the status of sites in each DMA, new sites identified and prioritized, costs, schedule, and other logistics. Develop and annual goal for restoration (e.g., number of trees planted, miles restored, etc.). Outreach covered under the Education and Outreach Section. | The RM continues to work with the BCRI and local communities to develop and implement riparian restoration programs and remove invasive species. New sites for restoration were identified, surveyed, and mapped (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=82ba0e2dd6424e35b46cf24bf2dcb1aa). In addition, we continue to work with and coordinate the County Weed Management Agency to identify and implement projects for invasive species removal near the Expo Center, in the Table Rock (Central Point) area, and within the Almeda fire footprint. A map of the work being completed was developed and is being updated as new areas are completed or areas are re-treated (https://rvcog.maps.arcgis.com/home/webmap/viewer.html?webmap=7c74710f96ed4742b5f2c8b917f1ff18). The maps also contain updates of project activities, status, and progress. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Volunteer Planting Event(s) | City participates in events: Events may include at least one featured tree planting project or tree giveaways to residents. Events will be planned in the community, as part of an event (e.g. Fall Festival, Earth Day), incorporated into Salmon Watch (riparian section), and/or planned as a regional event. | Staff time. RVCOG. Partners. And/or volunteers. | Document celebration activities, number of participants, number of trees planted and/or given away. | Annually | A minimum of one event held each year with local participants and activities that educate and implement tree planting. | Five volunteer events were held in the implementation year focused on restoration and planting. Three were focused on planting of restoration and fire sites and two were on site maintenance and restoration. Information on the events including number of volunteers, stakes planted, and other information can be found on the Volunteer Programs tab. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
| Maintain heathy streamside vegetation on publically owned lands | Seek opportunities to protect, or plant native trees and shrubs on public lands. | Staff time. Regional participation with RVCOG. Partnerships with local groups. | Track opportunities identified and projects implemented. | Annually as funding is available | Identify (map) Implemented projects on an annual basis until 100% complete. If all public lands are completed, maintain plantings and add any new areas that become public. | New sites are identified and catalogued using Survey 1-2-3, Google Earth, and other methods. In addition, 15 sites were identified using Project Intake form following a workshop that was hosted by BCRI members including the RM. Sites were submitted by Medford, Central Point, Phoenix, ODFW, RM, TFT, and others. The map of restoration projects is updated on a regular basis and continues to be. In 2023-2024, story maps which include the project maps were created to help with tracking all restoration and invasive species work by multiple partners (https://storymaps.arcgis.com/collections/2edc8e9d597a4f39a22b9d59a531c1de?item=1). Four story maps were created: 1. Restoration, 2. Riparian Condition Zones (Planning), 3. Invasive Species Management, and 4. General Information (other data). | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
Stormwater Runoff | Reduce warm stormwater runoff volumes (post construction). | Design and construct capital improvements that incorporate low impact development approaches to infiltrate and cool runoff & reduce other pollutants of concern. | Annual funding source from streets, as well as grant funds and private investments. | Tracking features installed for development, redevelopment and capital improvements. | Ongoing – development and project driven. | Annual Number of projects that incorporated LID or other methods into development and redevelopment plans | DMAs to fill in from P2 Program. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025
New Approaches and Projects |  | Explore new projects and program innovations to meet the goals of the Temperature TMDL. Part of the regional role includes coordination with other programs and organizations who are working in similar programs. Coordination has led to new projects, programs, partners, funding sources, training opportunities, and other innovations to improve TMDL programs and help move toward attaining goals including identification of new invasive species of concern and control methods and new restoration techniques.. | Staff time. Regional programs through RVCOG. | New approaches will be in response to new technology, innovations or adaptive management. Can include attending trainings or workshops. | Annually, as appropriate | New approaches will be identified with success indicators determined. Report on trainings and workshops attended. | The focus of adaptive management related to restoration has been in developing strategies for restoring riparian areas using the Riparian Condition Zone model which developed general strategies for the entire Bear Creek Corridor focused on balancing multiple needs including wildlife and aquatic habitat benefits, water quality including providing shade. controlling invasive species, encouraging growth and re-growth, restoring pollinator habitat and floodplain function, building in fire and climate resiliency, access for fire fighting, considering public safety, recreation, the unhoused population, and other factors. A restoration workshop was held on June 13th (20 attendees) to provide an overview of the Natural Resources Plan and identification of projects that are included on the Restoration map. | Year 1: July 2020-June 2021
Year 2: July 2021-June 2022
Year 3: July 2022-June 2023
Year 4: July 2023-June 2024
Year 5: July 2024-June 2025